## karnataka_irrigation_projects_2
project_name | project_type | current_status | region | hectares_irrigated | water_allocation_tmc | primary_river | districts_benefitted | taluks_benefitted | primary_purpose | dpr_approval_date | dpr_approval_amount | revised_approval_date | revised_approval_amount | expenditure_mar_2024 | completion_percentage | cost_variance_crores | nabard_loan | key_infrastructure | canals | additional remarks | latitude & longitude | latitude | logitude
Ghataprabha Left Bank Canal Modernisation | Modernisation | Completed | North Karnataka | 310823 |  | Ghataprabha | ['Belagavi', 'Bagalkot'] | ['Athani', 'Chikkodi', 'Gokak', 'Hukkeri', 'Raibag', 'Ramdurg', 'Savadatti', 'Badami', 'Bagalkot', 'Bilagi', 'Hunagund', 'Jamakhandi', 'Mudhol'] | Irrigation, Modernisation | 06.12.2018 | 573.28 | 09.10.2023 | 833 | 579.4 | 69.6 | -253.6 |  | Canal lining and structures | ['main canal of Ghataprabha (selected reaches in 0.00 to 109.00 km)', 'Gokak Canal (0.00 to 20.00 km)', 'Saidapura Canal (0.00 to 24.00 km)', 'South Canal (selected reaches in 0.00 to 45.00 km)', 'Bilagi Branch Canal (selected reaches in 0.00 to 49.00 km)'] |  | 16.16781522305941, 74.65493199955361 | 16.16781522305941 | 74.65493199955361
Udyana Kashi at Hidkal Dam | Eco-Tourism | Under Progress | Unknown | [5 empty] | create space for eco-tourism | 07.03.2022 | 147 | [6 empty] | parks, themed gardens, musical fountain, museum, planetorium & scientific centre, amusement parks, adventure sports park, skill centre, tourist information centre, cafeteria, hotels and restuarants |  | Utilizes 400 acres space below Hidkal dam. Out of total 07 works under the first phase, tender process for Package-I has been completed and order has to be issued. Remaining package works are at various stages of the tender process. Includes information on Rajalakham Gowda. | 16.14158933439945, 74.5993316286537 | 16.14158933439945 | 74.5993316286537
Hippargi Irrigation Project | Lift Irrigation Scheme | Under Progress | North Karnataka | 74742 |  |  | ['Belagavi', 'Bagalkot'] | ['Athani', 'Chikkodi', 'Jamakhandi'] | Irrigate land, avoid erosion of agricultural land | 04.10.1991 | 186.7 | 26.02.2008 | 1521.78 | 2783.36 | 100 | 1261.58 |  | 7 lift schemes, barrage, 500m long 15ft high retaining wall | Total length of canal is 306 km | All 7 lift schemes under the project are completed and the area of 74742 ha is brought under irrigation. Further, it is proposed to construct a 500m long 15ft high retaining wall on the left side downstream of the barrage to avoid erosion. | 16.555025689634657, 75.17004486075129 | 16.555025689634657 | 75.17004486075129
Murgod Lift Irrigation Scheme | Lift Irrigation Scheme | Nearing Completion | Unknown | 1939 |  | Markandeya |  |  | Irrigation | 17.04.2007 | 22.536 |  |  | 32.83 |  |  |  |  | Markandeya right bank canal | Lifting of water from 55th km of Markandeya right bank canal (near Malagali village) to irrigate area in 8 villages. | 15.886344133834498, 74.92702110597986 | 15.886344133834498 | 74.92702110597986
Chachadi Lift Irrigation Scheme | Lift Irrigation Scheme | Nearing Completion | Unknown | 2718 |  | Markandeya |  |  | Irrigation | 17.04.2007 | 24.06 |  |  | 21.13 |  |  |  | headwork | Markandeya right bank canal | Contract for the headwork and initial 5.00 km. | 15.923605598913797, 74.8610011254369 | 15.923605598913797 | 74.8610011254369
Doodhganga Project | Irrigation Project | Under Progress | Unknown | 59933 |  | Doodhganga |  |  | Irrigation |  |  |  |  | 361.07 |  |  |  | Composite Dam | [{'name': 'Nidhori', 'length_km': 21.57, 'status': 'Completed'}, {'name': 'Bidari', 'length_km': 25.155, 'status': 'Under Progress'}, {'name': 'Dattawad', 'length_km': 30.0, 'status': None}] | Inter-state project of Maharashtra and Karnataka. Dam located near Asangaon village of Rathnagiri taluk in Kolhapur District of Maharashtra state. | 16.707760033044107, 74.24987334054683 | 16.707760033044107 | 74.24987334054683
Bellary Nala Project | Irrigation Project | Under Progress | North Karnataka | 8200 |  | Bellary nala | ['Belagavi'] | ['Belagavi', 'Gokak', 'Saundatti', 'Bailahongal'] | Irrigation | 17.01.2005 | 635.5 |  |  | 318.78 |  |  |  | ['Dam'] | Main canal with total length of 106 km. | Bellary nala is a main tributary to Markendaya River. Dam foundation in block 1 to 6 and 8 to 18 are partly completed. Works in main canal from km 44 to 106 are under progress, excluding works in forest areas from km 1 to 10 and 32 to 40. | 15.839621367068691, 74.54363017951177 | 15.839621367068691 | 74.54363017951177
Kinaye Project | Dam Construction | Nearing Completion | North Karnataka | 1475 |  | Mangothri River | ['Belagavi'] |  | Irrigation | 28.09.2010 | 35.43 | 22.11.2013 | 79 | 94.51 | 100 | 15.51 |  | ['Dam', 'Canal Network'] |  | Near Kinaye village | 15.79420360801706, 74.48409626573054 | 15.79420360801706 | 74.48409626573054
Tubachi - Babaleshwar Lift Irrigation Scheme | Lift Irrigation Scheme | Under Progress | North Karnataka | 52700 | 6.3 | Krishna River | ['Belagavi', 'Bagalkot'] | ['Vijayapur', 'Athani', 'Jamakhandi'] | Irrigation | 28.02.2014 | 2488.97 | 21.07.2017 | 3572 | 3120.85 | 87.4 | -451.15 |  | head works | head works, west main canal, east main canal, north main canal, south main canal, distributaries |  | 16.60908525256784, 75.26555065594523 | 16.60908525256784 | 75.26555065594523
Basaveshwar (Kempwad) Lift Irrigation Scheme | Lift Irrigation Scheme | Under Progress | North Karnataka | 27462 | 4 | Hipparagi Barrage backwaters | ['Belagavi District'] | ['Athani Taluk'] | Irrigation of drought-affected villages | 22.06.2016 | 1120.36 |  |  | 1101.93 |  |  |  | Hipparagi Barrage |  | Proposed to irrigate 22 drought affected villages coming under northern part of Athani Taluk, near Ainapur village. | 16.759283053512963, 74.89678139852218 | 16.759283053512963 | 74.89678139852218
Venkateshwar Lift Irrigation Scheme | Lift Irrigation Scheme | Under Progress | Unknown | 7200 |  |  |  | ['Mudhol', 'Jamakhandi'] | Irrigation | 12.02.2015 | 174.42 |  |  | 112.88 | [5 empty] | Benefitting 10 villages (4 villages of Mudhol and 6 villages of Jamakhandi taluk). | 15.53282825122386, 79.95283410693416 | 15.53282825122386 | 79.95283410693416
Improvements to Chikkodi Branch Canal | Modernisation | Nearing Completion | Unknown | 11481 |  |  |  |  | To provide water to 11481 ha of land and facilitate irrigation to the subsequent command | [8 empty] | Chikkodi Branch Canal | Chikkodi Branch Canal (88 km long, first 30 km being improved) | The 88 km long Chikodi Branch Canal was completed in 1984 and irrigates 33403 ha of land. Improvements are to the first 30 km of the now dilapidated canal. | 16.42947614304262, 74.58781239217092 | 16.42947614304262 | 74.58781239217092
Filling of 17 tanks of 10 villages and additional 22 tanks of Raibag taluk in Belgavi | Tank Filling Scheme | Under Progress | North Karnataka |  |  | Krishna River | ['Belagavi'] | ['Raibag'] | Solve the drinking water problem and assist in ground water recharge | 26.07.2017 | 91.4 |  |  | 87.73 |  |  |  | 39 tanks |  | Project involves filling 39 tanks (17 tanks of 10 villages and 22 additional tanks) to 50% of their storage capacity. The area faces severe stress for drinking water due to reduced inflow to tanks. | 16.493907682224865, 74.77419374318471 | 16.493907682224865 | 74.77419374318471
Filling of 19 tanks of 10 villages of Kudachi constituency of Raibag taluk in Belagavi | Tank Filling Scheme | Under Progress | North Karnataka |  |  | Krishna River | ['Belagavi'] | ['Raibag'] | To solve the drinking water problem of the area by filling these tanks to 50% of their storage capacity and also assist in ground water recharge. | 27.04.2017 | 34.38 |  |  | 24.43 |  |  |  | 19 tanks |  | Project addresses severe drinking water stress in Bastwad, Kandal, Katakabhavi, Devapura hatti, Nidagundi, Savasudi, Moraba, Nilaji, Suttatti and Harogeri villages in Kudachi constituency, Raibag taluk, Belagavi district due to reduction in inflow to the tanks over the years. | 16.494236876936696, 74.77166173800092 | 16.494236876936696 | 74.77166173800092
Kullahalli Hunnur LIS | Lift Irrigation Scheme | Under Progress | Unknown | 9163.63 | 0.88 | Krishna River |  | ['Jamkhandi'] | to stabilise the suffering atchkat of 9163.63 Ha under the downstream of Jamakhandi branch canal Ch.20+650 (Maigur Chowki) and surrounding villages in Jamkhandi during the Khariff season | 21.12.2017 | 73.75 |  |  | 29.77 |  |  |  |  | ['Jamakhandi branch canal'] | Jamakhandi branch canal starts at km 70 (Chimmad Chowki) of GLBC. The project is proposed to stabilise the suffering atchkat under the downstream of Jamakhandi branch canal Ch.20+650 (Maigur Chowki). | 16.526395608448315, 75.16410046513404 | 16.526395608448315 | 75.16410046513404
Godchinamalki LIS | Lift Irrigation Scheme | Nearing Completion | Unknown | 2568.42 | 0.471 | ['Ghataprabha River', 'Markandeya River'] |  | ['Gokak taluk'] | Irrigation | 08.01.2018 | 107.16 |  |  | 82.3 | [5 empty] | Stage-I irrigates 1031.51 ha by lifting 0.191 TMC from Ghataprabha River. Stage-II irrigates 1537.91 ha by lifting 0.280 TMC from Markandeya River. A total of 12 villages are benefitted. | 16.132090447674646, 74.7303142394568 | 16.132090447674646 | 74.7303142394568
Strengthening and raising of Galgali barrage | Modernisation | Nearing Completion | North Karnataka | 7448 | 1.244 | Krishna | ['Bagalkot', 'Vijayapura'] | ['Bilagi'] | Irrigation and Drinking Water Supply | 07.02.2018 | 32 |  |  | 42.29 |  |  |  | Galgali Bridge cum Barrage |  | Barrage constructed in 1973. Original storage capacity 0.569 TMC. Target storage capacity 1.244 TMC. | 16.340483490618055, 75.6296681619161 | 16.340483490618055 | 75.6296681619161
Kittur Tank Filling Scheme | Tank Filling Scheme | Under Progress | Unknown |  |  |  |  | ['Kittur', 'Bailhongal'] | Solve drinking water problem and assist in ground water recharge by filling tanks | 08.11.2017 | 248.2 |  |  | 139.97 |  |  |  | 64 tanks |  | Proposed to fill 64 tanks to 50% of their storage capacity due to reduction in inflow and severe stress for drinking water. | 15.598805568573184, 74.78881764023448 | 15.598805568573184 | 74.78881764023448
Jalalpura (Old Diggewadi) bridge cum barrage | Barrage Construction, Drinking Water Scheme | Under Progress | Other Regions |  | 0.176 | Krishna River | ['Belgavi'] | ['Raibag', 'Chikkodi'] | provide drinking water facility, provide communication | 17.10.2019 | 27.93 | [6 empty] | bridge cum barrage |  | Store 0.176 TMC of water to provide drinking water facility to 16 villages of Raibag and Chikkodi taluk. The bridge cum barrage will also assist in daily activities of the villagers. | 13.69143567745923, 76.96261758207405 | 13.69143567745923 | 76.96261758207405
Ghatti-Basavanna Drinking Water Scheme | Drinking Water Scheme | Under Progress | Unknown |  | 5.96 | Markandeya River |  | ['Hukkeri', 'Bailahongal', 'Savadatti'] | ['Drinking water supply', 'Tank filling', 'Industrial water supply', 'Flood management'] | 24.11.2020 | 990 |  |  | 9.9 |  |  |  | ['Dam on Markandeya River'] |  | The scheme proposes to store a total of 5.96 TMC, including 2.76 TMC for drinking water requirements of Gokak and surrounding 131 villages. The dam is to be constructed downstream of the confluence of Markandeya and Ballari Nala. | 16.159074024244315, 74.81406186736957 | 16.159074024244315 | 74.81406186736957
Sri Adavisiddeshwara Lift Irrigation Scheme | Lift Irrigation Scheme | Under Progress | Unknown | 1200 | 0.11 | Hiranyakeshi River |  | ['Hukkeri'] | irrigation facility | 20.11.2020 | 66.13 | [6 empty] | delivery chamber at Gajabarwadi |  |  | 16.215847073049098, 74.35701895323307 | 16.215847073049098 | 74.35701895323307
Sri Shankarlinga Lift Irrigation Scheme | Lift Irrigation Scheme | Under Progress | Unknown | 1200 | 0.11 | Hiranyakeshi River |  | ['Hukkeri'] | Irrigation | 06.03.2021 | 67.4 | [8 empty] | Proposed to lift water near Kochari village. Benefits Jabapura, Nerli, Masaraguppi and Arjunwad villages. | 16.215847073049098, 74.35701895323307 | 16.215847073049098 | 74.35701895323307
Sasalatti-Shivalingeshwara Lift Irrigation Scheme-1 | Lift Irrigation Scheme | Under Progress | North Karnataka | 22918.57 | 4.03 | Krishna River | ['Bagalkote'] | ['Jamakhandi', 'Mudhol', 'Bilagi', 'Rabakavi-Banahatti'] | providing irrigation facility | 29.01.2022 | 266 |  |  | 161.91 |  |  |  |  | ['Ghataprabha left bank canal (GLBC km 63.00 to 103.00)'] | Water is lifted from Krishna River near Halingali village to provide irrigation to suffering atchkat. | 16.56499574461871, 75.18125584984489 | 16.56499574461871 | 75.18125584984489
Sasalatti-Shivalingeshwara Lift Irrigation Scheme-2 | Lift Irrigation Scheme | Yet to Start | North Karnataka | 9640.7 | 1.67 | Krishna River | ['Bagalkote'] | ['Rabakavi-Banahatti'] | Providing irrigation facility | 01.12.2022 | 209 | [7 empty] | Ghataprabha left bank canal (GLBC km 52.00 to 63.00) | Designed for providing irrigation facility to suffering atchkat of Ghataprabha left bank canal (GLBC km 52.00 to 63.00) by lifting water near Halingali village. Tender process for the first phase of the work has been completed and the work is yet to be started. Action is being taken to invite tenders for the second stage. | 16.60382792571113, 77.51735261075419 | 16.60382792571113 | 77.51735261075419
Mantur-Mahalakshmi Lift Irrigation Scheme | Lift Irrigation Scheme | Nearing Completion | North Karnataka | 12007.14 | 2.06 | Krishna River | ['Bagalkote'] | ['Mudhol', 'Bilagi'] | providing irrigation facility | 29.01.2022 | 228 |  |  | 228.37 |  |  |  |  | Ghataprabha left bank canal (GLBC km 103.00 to 109.00) |  | 16.744491800152776, 74.76937110409536 | 16.744491800152776 | 74.76937110409536
Kallol Yadur bridge cum barrage | Barrage Construction | Under Progress | North Karnataka |  |  | Krishna River | ['Belagavi'] | ['Chikodi'] | Irrigation and drinking water requirements | 04.02.2022 | 35 | [6 empty] | Bridge cum barrage (155.00m long, 62 vents) |  | Original bridge cum barrage constructed during 1981-82. Located downstream of the confluence of Krishna River, Doodhganga and Vedaganga River. Currently in dilapidated state, hence reconstruction is required. | 16.428529390594104, 74.5884132069603 | 16.428529390594104 | 74.5884132069603
Shirur LIS | Lift Irrigation Scheme | Tender Process | North Karnataka | 10224.57 |  | Ghataprabha River | ['Bagalkote District'] | ['Badami', 'Bagalkote'] | Provide irrigation to suffering atchkat | 03.08.2022 | 243 | [6 empty] | Lift irrigation system (pumping station, pipelines) | Ghataprabha Right Bank Canal | Project designed to provide irrigation to atchkat coming under km 182.560 to km 199.093 of Ghataprabha Right Bank Canal. Water lifted from Ghataprabha River near Mallapmar village in Bagalkote Taluka. Tender process for the first phase of the work has been completed and the work is yet to be started. Action being taken to invite tenders for second stage. | 18.825138283636623, 74.37752721073652 | 18.825138283636623 | 74.37752721073652
Anwal LIS | Lift Irrigation Scheme | Tender Process | North Karnataka | 14525.43 |  | Ghataprabha River | ['Bagalkote District'] | ['Badami', 'Bagalkote'] | Irrigation | 25.08.2022 | 411 | [6 empty] | Lift system near Devnal village | ['Kaladgi distributary', 'Anwal Distributary', 'Ghataprabha Right Bank Canal'] | Designed to provide irrigation to suffering atchkat. Tender process for the first phase of the work has been completed and the work is yet to be started. Action being taken to invite tenders for second stage. | 16.205299182891828, 75.50163179481562 | 16.205299182891828 | 75.50163179481562
Kagawad TFS | Tank Filling Scheme | Tender Process | Unknown |  |  |  |  | ['Kagawad Taluk'] | Solve the drinking water problem by filling tanks to 50% of their storage capacity and assist in ground water recharge. | 04.11.2022 | 229.4 | [6 empty] | 23 tanks |  | The region does not have a perennial river and has experienced reduction in inflow to tanks, leading to severe stress for drinking water. Tender process for the first phase of work has been completed, but work is yet to be started. Action is being taken to invite tenders for the second stage. | 16.69411974654307, 74.72233848981406 | 16.69411974654307 | 74.72233848981406
Ammajeshwari (Kottalgi) LIS | Lift Irrigation Scheme | Tender Process | Unknown | 9950 |  | Krishna River |  | ['Athani'] | Irrigation and Drinking Water Supply | 13.01.2023 | 1486.81 | [6 empty] | Lift Irrigation System |  | The villages in south east part of Athani taluk are on higher elevation and deprived from irrigation from Hipparagi and Tubachi-Bableshwar LIS. Severe stress for drinking water due to reduced tank inflow and alarming ground water depths. Beneficiary villages: Telsang, Kilaradaddi, Bhosalewadi, Kannal, Bannur, Kakamari and Kottalgi. Tender process for the first phase completed, work yet to start. Action being taken to invite tenders for second stage. | 16.726748138740533, 75.06118479036815 | 16.726748138740533 | 75.06118479036815
Arabhavi Tank Filling Scheme | Tank Filling Scheme | Tender Process | Unknown | [5 empty] | To solve the drinking water problem of the area by filling 20 tanks to 50% of their storage capacity and also assist in ground water recharge. | 10.01.2023 | 323.87 | [6 empty] | 20 tanks |  | Proposed to fill 20 tanks of Arabhavi Constituency. Severe stress for drinking water due to reduction in inflow. Tender process for the first phase of the work has been completed and the work is yet to be started. Action being taken to invite tenders for second stage. | 16.221308835082002, 74.82316027190794 | 16.221308835082002 | 74.82316027190794
Melligeri-Halagali LIS | Lift Irrigation Scheme | Tender Process | North Karnataka | 3535 |  | Krishna River | ['Bagalkote District'] | ['Mudhol', 'Bilagi'] | Provide irrigation to left out area during Khariff season | 13.01.2023 | 197 | [6 empty] | ['Galgali Barrage'] | ['Ghataprabha Left Bank Canal'] | Designed to provide irrigation to left out area during Khariff season. Water lifted from Krishna River downstream of Galgali Barrage. Tender process for the first phase of the work has been completed and the work is yet to be started. Action being taken to invite tenders for second stage. | 16.326731143863196, 75.2602991178786 | 16.326731143863196 | 75.2602991178786
Sri Channavrushabendra LIS | Lift Irrigation Scheme | Tender Process | North Karnataka | 11600 |  | Markandeya River | ['Belagavi'] | ['Bailhongala', 'Savadatti'] | provide irrigation facility | 10.01.2023 | 520 | [8 empty] | Proposed to lift water from right bank of Markandeya River near Paschapur village of Chikkodi Taluk. Provides irrigation facility to 31 villages. Tender process for the first phase of the work is under progress, and action is being taken to invite tenders for the second stage. | 16.359764121226394, 75.42533367699858 | 16.359764121226394 | 75.42533367699858
Mahalakshmi LIS | Lift Irrigation Scheme | Tender Process | North Karnataka | 6400 | 0.92 | Dudhganga River | ['Belagavi District'] | ['Chikkodi taluk'] | Provide irrigation facility to address reduction in crop yield due to reduced rainfall. | 13.01.2023 | 382.3 | [6 empty] | Kalol-Yediyur barrage |  | Farmers facing severe reduction in yield in Khariff crops due to reduction in rainfall. Tender process for the first phase completed, work yet to be started. Action being taken to invite tenders for second stage. | 16.559511361419876, 74.4461024570623 | 16.559511361419876 | 74.4461024570623
Mareguddi LIS | ['Lift Irrigation Scheme', 'Drinking Water Scheme', 'Tank Filling Scheme'] | Under Progress | Unknown | 2035 | 0.39 |  |  | ['Jamkhandi', 'Mudhol'] | To provide irrigation facility, solve drinking water problem, and assist in ground water recharge. | 23.02.2023 | 216.5 | [6 empty] | ['Galgali barrage', '5 tanks', '31 check dams'] |  | The land in Jamkhandi Taluka is fertile but falls under low rainfall area and lacks sufficient irrigation facility. The DPR of the project is administratively approved. | 16.425100094464558, 75.339212128934 | 16.425100094464558 | 75.339212128934
Kadarkoppa LIS | Lift Irrigation Scheme | Under Progress | Unknown | 8750 |  | Ghataprabha River |  | ['Mudhol', 'Bilagi'] | Provide irrigation to suffering atchkat | 27.03.2023 | 265 | [6 empty] | Lift system/Pumping station | ['Ghataprabha Right Bank Canal'] | Designed to provide irrigation to atchkat under km 139.00 to km 145.00 of Ghataprabha Right Bank Canal. Water supplied to Ghataprabha Right Bank Canal near Kadarkoppa village. Estimate and DTP for the work is under preparation. | 16.133879432414318, 75.41307444614283 | 16.133879432414318 | 75.41307444614283
Kargaon LIS | Lift Irrigation Scheme | Under Progress | Unknown | 8390 |  | Krishna River |  | ['Chikkodi'] | To irrigate 8390 ha of area in Khariff season in 14 villages of Chikkodi taluk on the left side of Chikkodi branch canal. | 14.03.2023 | 567 | [7 empty] | ['Chikkodi branch canal'] | The project aims to irrigate the left side of the Chikkodi branch canal, which was previously unirrigated despite fertile land. Water will be lifted from Krishna River near Kallol village of Chikkodi taluka during monsoon season. Estimate and DTP for the first phase work is under preparation. | 16.336788142266094, 74.6333993223032 | 16.336788142266094 | 74.6333993223032
Flood management works from downstream of Gokak falls to Lolsur Bridge near NH-31, Floor protection works to protect Gokak town and nearby villages from the floods of Ghataprabha River and River front development works | Flood Management | Tender Process | Unknown |  |  | Ghataprabha River |  | ['Gokak'] | To protect Gokak town and nearby villages from the floods of Ghataprabha River during monsoon season and to promote tourism in and around Gokak. | 14.03.2023 | 685 | [8 empty] | Tender process for the first phase of the work is under progress. | 16.339847875005827, 75.25789491743272 | 16.339847875005827 | 75.25789491743272
Uchagaon and Santibastavad Tank Filling Scheme | Tank Filling Scheme | Under Progress | Unknown |  |  | Malaprabha and Markandeya River |  |  | To solve the drinking water problem of the area and assist in ground water recharge by filling tanks. | 12.02.2024 | 287.55 | [5 empty] | 200 | Reservoir |  | Proposed to fill 12 tanks in Uchagaon Hobli and 08 tanks in Santibastavad village to 50% of their storage capacity. Provides drinking water facility for 09 villages. Tender has been invited. | 16.16340195325057, 74.79506869083316 | 16.16340195325057 | 74.79506869083316
Modernisation of Malaprabha Main Canal and Distributaries | Modernisation | Nearing Completion | North Karnataka | 196132 |  | Malaprabha river | ['Belagavi', 'Dharwad', 'Gadag', 'Bagalkot'] | ['Saundatti'] | Provide irrigation facility and ensure efficient water supply to tail end areas. | 17.08.2017 | 1120 | 30.10.2019 | 1000 | 2132.02 | 100 | 1132.02 |  | ['Dam (across Malaprabha river)'] | ['Malaprabha Main Canal', 'Distributaries', 'Sub Distributaries'] | The Malaprabha main canal and distributaries were constructed 35 years ago and had dilapidated in reaches, making it difficult to provide water to the tail end, necessitating modernization. | 15.769593344316664, 74.90200465009922 | 15.769593344316664 | 74.90200465009922
Kalasa Nala and Bandura Nala Diverstion Project | Drinking Water Scheme, Diversion Project, Lift Irrigation Scheme | Yet to Start | Unknown |  | 3.9 | Kalasa Nala, Bandura Nala, Haltara Nala, Surla Nala |  |  | Drinking Water Supply | 27.03.2023 | 995.3 | [6 empty] | low elevation diversion dams, jackwell, rising main, pump house |  | The Mahadayi Tribunal gave its final verdict on 14.08.2018. The Central Government issued a Special Gazette Notification dated 27.02.2020 regarding the final judgment. Detailed Project Reports (DPRs) for the said projects were approved by the Central Water Commission on 29.12.2022. The administrative approval amount of Rs. 995.30 crore is specifically for the Kalasa Nala Diversion Scheme. The Bandura Nala Diversion Project also received administrative approval on 27.03.2023, but no specific amount was mentioned for it. Water allocation includes 1.72 TMC released under Kalasa Nala Diversion Project and 2.18 TMC to be allocated under drinking water sharing and Bandura Nala diversion project for the state of Karnataka. | 15.493663227505415, 74.04845651630018 | 15.493663227505415 | 74.04845651630018
Shiggaon Lift Irrigation Scheme | Lift Irrigation Scheme | Dedicated to Nation | Central Karnataka | 13500 |  |  | ['Haveri'] | ['Shiggaon', 'Savanur', 'Hanagal'] | Irrigation, Drinking water supply, Tank filling |  |  |  |  | 511.95 |  |  |  | Sprinkler irrigation system, Drip irrigation system, 18 tanks, 39 tanks |  | Sprinkler irrigation system for 9900 ha is completed. Estimates are under preparation for providing drip irrigation to the balance area of 3600 ha adopting Madhya Pradesh model. The scheme of filling 18 and 39 tanks under this project is completed. | 15.436303545147702, 75.02803653873917 | 15.436303545147702 | 75.02803653873917
Savanur Lift Irrigation Scheme | Lift Irrigation Scheme | Under Progress | Unknown | 15500 | 1.5 | Varada River |  | ['Savanur taluk'] | Irrigation and tank filling |  |  |  |  | 262.66 |  |  |  | 9 tanks, 39 additional tanks |  | Proposed to irrigate 15500 ha in 30 villages of Savanur taluk and filling of 09 tanks. Works of filling of 9 tanks and 39 additional tanks are completed. Estimates are under preparation for providing drip irrigation to 3600 ha adopting Madhya Pradesh model. Water lifted from Varada River near Kalasuru village. | 14.481721611776308, 75.00990765437567 | 14.481721611776308 | 75.00990765437567
Modernisation of Kolachi Right Bank Canal | Modernisation | Nearing Completion | North Karnataka | 5877 |  | Malaprabha River | ['Belagavi'] | ['Ramadurga'] | Irrigation | 27.04.2015 | 101.04 | [6 empty] | Kolachi Wier | [{'name': 'Kolachi Right Bank Canal', 'length_km': 49}] | The original project was completed long before. Modernization works are taken up in 05 packages, and 04 package works are completed. | 15.93681686710636, 75.35125965408771 | 15.93681686710636 | 75.35125965408771
Filling of tanks from Tuparihalla | Tank Filling Scheme | Under Progress | Central Karnataka |  | 0.164 | Tuparihalla | ['Dharwad'] | ['Dharwad'] | Filling MI tanks | 30.03.2017 | 22.5 | [6 empty] | MI tanks of Tadakoda, Bhokyapura, Garaga, Halethegooru, Bogooru and Neeralakatti villages |  | The DPR of the project is administratively approved. | 15.580785296278908, 74.92548408291866 | 15.580785296278908 | 74.92548408291866
Filling of tanks and bandharas of Haliyala taluk of Uttara Kannada | Tank Filling Scheme | Under Progress | Other Regions |  | 0.812 | Kali River | ['Uttara Kannada'] | ['Haliyal'] | to provide irrigation to the farmers during summer and to provide drinking water to people and cattle during January to June and to replenish ground water level | 29.06.2017 | 220 |  |  | 127.39 |  |  |  | 46 tanks and 19 barrages |  |  | 14.873971566853449, 74.24205471766253 | 14.873971566853449 | 74.24205471766253
Filling of MI tanks of Kalaghatagi taluk in Dharwad district from Bedti river | ['Tank Filling Scheme', 'Lift Irrigation Scheme', 'Drinking Water Scheme'] | Under Progress | Central Karnataka |  | 0.449 | Bedti river | ['Dharwad'] | ['Kalaghatagi'] | to provide irrigation, provide drinking water to people and cattle around the tanks, to replenish ground water level and to facilitate agricultural activities | 17.08.2017 | 125 |  |  | 71.51 |  |  |  | barrage across the river Bedti near Belavantara village |  | It is proposed to fill 35 tanks of Kalaghatagi taluk to 50% of their total storage capacity. | 14.902044386295255, 74.79146179448779 | 14.902044386295255 | 74.79146179448779
Filling of 129 tanks in Mundgod taluk | Tank Filling Scheme | Under Progress | Other Regions |  | 1.48 | Bedthi River | ['Uttara Kannada District'] | ['Mundgod taluk'] | To fill tanks in drought prone areas | 08.03.2018 | 289.1 |  |  | 156.6 |  |  |  | 129 MI tanks |  | Tanks to be filled upto 50% of its capacity. | 14.89412578624326, 74.78872916808659 | 14.89412578624326 | 74.78872916808659
Filling of 84 tanks in Mundgod taluk | Tank Filling Scheme | Nearing Completion | Other Regions |  | 0.2 | Bedthi River | ['Uttar Kannada'] | ['Mundgod'] | To solve the drinking water problem of the area by filling tanks to 50% of their storage capacity and assist in ground water recharge. | 08.11.2019 | 225 |  |  | 166.84 |  |  |  | 84 MI / ZP tanks | Kavalagi halla (distributary) | Project proposes to fill 84 MI / ZP tanks in 05 Gram Panchayats (Malagi, Phala, Katturu, Khodambi and Onnikeri). Severe stress for drinking water due to reduction in inflow to tanks over the years. | 14.89674213454341, 74.78390233443622 | 14.89674213454341 | 74.78390233443622
Bagewadi Tank Filling Scheme | Tank Filling Scheme | Under Progress | Other Regions |  | 0.469 | Malaprabha River | ['Belgavi'] |  | fill 62 nos of Tanks and provide bulk water supply for 47 villages | 16.01.2019 | 379.92 | 12.02.2024 | 519.1 | 46.19 | 8.9 | -472.91 |  | ['Impounding Reservoir'] |  | Due to non-availability of land for Impounding Reservoir the design of the project has been altered. | 16.159448059293116, 74.79148378689973 | 16.159448059293116 | 74.79148378689973
Hingaraga Tank Filling Scheme | Tank Filling Scheme | Tender Process | North Karnataka |  | 0.175 | Markandeya River | ['Belagavi'] | ['Belagavi'] | Solve drinking water problem and assist in ground water recharge by filling tanks to 50% of their storage capacity | 03.10.2019 | 143.53 | [6 empty] | 13 tanks |  | Due to reduction in inflow over the years to 13 tanks in Hingaragi Hobli of Belagavi taluk, there is a severe stress for drinking water in the area. | 16.167168539092145, 74.80358808902484 | 16.167168539092145 | 74.80358808902484
Construction of Retaining wall near Hampihole village in Ramdurga Taluk | Flood Management | Under Progress | Unknown |  |  | Malaprabha River |  | ['Ramdurga Taluk'] | To protect the people and livestock of Hampihole, Avaradi, Maradgi and Sureban villages from the floods of Malaprabha River | 16.06.2021 | 126 | [6 empty] | Retaining wall |  | Beneficiary villages: Hampihole, Avaradi, Maradgi, Sureban. DPR administratively approved. | 16.159561413702463, 74.79138722738 | 16.159561413702463 | 74.79138722738
Sri Veerabhadreshwar Lift Irrigation Scheme | Lift Irrigation Scheme | Under Progress | Unknown | 17377 | 2.5 | Ghataprabha River |  | ['Mudhol', 'Ramdurga'] | Irrigation and tank filling | 21.01.2015 | 544 |  |  | 298.88 |  |  |  | 10 minor tanks |  |  | 16.34643688180103, 75.24553529890831 | 16.34643688180103 | 75.24553529890831
Salapura LIS | Lift Irrigation Scheme | Under Progress | North Karnataka | 13000 |  | Ghataprabha River | ['Bagalkot'] | ['Ramadurga', 'Badami', 'Mudhol'] | To irrigate land deprived from irrigation by Rameshwara & Veerabhadreshwara LIS | 07.03.2018 | 566 |  |  | 261.06 | [5 empty] | Works to be taken up in two stages (Rs.327.00 crores & Rs.239.00 crores). Water is lifted near Chikkur Thanda of Mudhol taluk. Irrigates 10878 ha from 19 villages of Ramadurga taluk, 1832 ha from 6 villages of Badami taluk, and 290 ha from 2 villages of Mudhol taluk. | 16.320079521997837, 75.24690858985547 | 16.320079521997837 | 75.24690858985547
Replacement of PSC pipes in 7 LIS s in Nargund Constituency | Lift Irrigation Scheme | Tender Process | Unknown |  |  | Bennehalla and Malaprabha |  | ['Nargund'] | To provide irrigation to the designate atchkat by replacing dilapidated PSC pipes | 19.08.2022 | 80 | [6 empty] | PSC pipes |  | The scheme proposes to replace dilapidated PSC pipes in Banahatti, Kurlageri, Surkod, Khanapura, Raddernagnur, Kolachi and Konnur LIS. These LIS are constructed across Bennehalla and Malaprabha. The dilapidated pipes have prevented irrigation to the designated atchkat. | 15.681300129989973, 75.47528724053119 | 15.681300129989973 | 75.47528724053119
Tuparihalla Flood protection works | Flood Management | Under Progress | Unknown |  |  | Tuparihalla |  |  | To protect the villages and farmlands around the Tuparihalla by taking up flood management & flood protection works. | 19.03.2022 | 312 | [8 empty] | Chikkahalla, Kallahalla, Bannihalla, Hunasikattehalla and Gadnyahalla are some of the major tributaries of the total 49 tributaries of Tuparihalla. The area around gets flooded every year due to unseasonal rains. Works of first phase are under progress. | 15.580919645775946, 74.92517294668845 | 15.580919645775946 | 74.92517294668845
Sattigeri LIS | Lift Irrigation Scheme | Tender Process | North Karnataka | 6768 | 1 | Ghataprabha River | ['Belagavi District'] | ['Savadatti taluk'] | Irrigation | 12.01.2023 | 546 | [8 empty] | The farmers of Savadatti taluk, Belagavi District rely on rainfall for growing their crops. Due to reduction in rainfall in recent years, the farmers in Savadatti taluk, Belagavi District are facing severe reduction in yield of crops and are requesting to provide irrigation facility to their lands. Water is lifted from Ghataprabha River near Talkatnal village of Gokak Taluk. | 16.350390179209732, 75.24141542606684 | 16.350390179209732 | 75.24141542606684
Kiravatti TFS | Tank Filling Scheme | Tender Process | Other Regions |  |  | Bedthi River | ['Uttarakannada'] | ['Yallapura', 'Mundgod'] | Solve the drinking water problem by filling tanks to 50% of their storage capacity and assist in ground water recharge | 12.01.2023 | 274.5 | [6 empty] | Lifting water from Bedthi River near Banksali village (near Shidlagundi bridge) to fill 100 tanks |  | Tanks in the area are not getting filled due to streams and tanks located in ridges and reduction in inflow due to development works in catchment, leading to severe stress for drinking water. The project aims to fill 100 tanks in the region. | 14.897443640085696, 74.78460929524513 | 14.897443640085696 | 74.78460929524513
Amruth Sarovara Project | Drinking Water Scheme | Tender Process | Central Karnataka |  |  |  | ['Hubli', 'Dharwad'] | ['Annigeri', 'Navalagunda', 'Kundagola', 'Hubbali', 'Dharwad', 'Alnawara', 'Kalghatgi'] | Rejuvenate and undertake comprehensive development of tanks to mitigate severe stress on drinking water in the region. | 12.01.2023 | 30 | [6 empty] | tanks |  | Project falls under Hubli-Dharwad Parlimentary Constituency. | 14.994408424388403, 75.91295604963983 | 14.994408424388403 | 75.91295604963983
Upper Tunga Project | Irrigation Scheme | Nearing Completion | Central Karnataka | 80494 |  | Tunga River | ['Davanagere', 'Shivamogga', 'Haveri'] | ['Shimoga '] | Provide irrigation facilities | 30.10.1992 | 271.41 | 16.03.2023 | 3395.02 |  |  |  |  | ['New Dam across Tunga River', 'Existing Tunga Anicut'] | [{'name': 'Upper Tunga Main Canal', 'length_km': 258.0, 'status': 'Completed'}, {'name': 'Distributaries (5 out of 6)', 'status': 'Completed'}, {'name': 'Distributary-6 (Dy-6)', 'status': 'Nearing Completion'}] |  | 13.712202364678397, 75.40466322873587 | 13.712202364678397 | 75.40466322873587
Modernisation of Tunga Anicut | Modernisation | Nearing Completion | Unknown |  |  | Tunga |  |  | Modernisation | 28.06.2012 | 309 |  |  | 319.13 |  |  |  | Tunga Anicut | left & right bank canal of Tunga Anicut | The works are taken up in two packages. | 13.740217849628268, 75.40740981063018 | 13.740217849628268 | 75.40740981063018
Sasvehalli Tank Filling Scheme | Tank Filling Scheme | Under Progress | Coastal & Malnad |  |  | Tungabhadra River | ['Davanagere', 'Shivamogga', 'Chitradurga'] | ['Channagiri', 'Davanagere', 'Honnali', 'Shivamogga', 'Chitradurga', 'Holalkere'] | Tank Filling | 11.01.2017 | 415.68 | [6 empty] | ['Sasvehalli Lift Irrigation Scheme (LIS)', 'Shantisagara tank', '92 tanks'] |  | The project is executed in 2 stages. Stage 1 fills 43 tanks (27 in Channagiri taluk, 11 in Davanagere taluk, 4 in Honnali constituency, 1 in Shivamogga rural constituency) from Tungabhadra River. Stage 2 lifts water from Shantisagara tank to fill 49 tanks (24 in Channagiri taluk, 19 in Davanagere taluk, 3 in Chitradurga taluk, 3 in Holalkere constituency). | 15.470031221805687, 76.68239337914815 | 15.470031221805687 | 76.68239337914815
Augmentation of Sasvehalli Tank Filling Scheme | Tank Filling Scheme | Under Progress | Unknown | [5 empty] | To make good the shortfall in water requirement for filling up the tanks due to variation in tank capacity. | 25.06.2021 | 167 | [6 empty] | additional rising main parallel to the existing rising main |  | Scheme addresses shortfall in water requirement for tank filling due to variation in tank capacity. | 14.153314887561413, 75.71407195829558 | 14.153314887561413 | 75.71407195829558
Kachavi Tank Filling Scheme | Tank Filling Scheme | Nearing Completion | Coastal & Malnad |  | 0.15 | Varada River | ['Shivamogga'] | ['Soraba'] | Augment scarcity of water in 11 villages by feeding 21 tanks | 18.12.2012 | 16.5 |  |  | 10.74 |  |  |  | Kachavi Tank, Lift system |  | Benefits 11 villages by feeding 21 tanks. | 14.587005302135303, 75.25336972725162 | 14.587005302135303 | 75.25336972725162
Development of Kanaka Sarovara (Doddakere) in Kaginele village | Eco-Tourism | Nearing Completion | Unknown | [5 empty] | Comprehensive development of the tank for recreational and cultural purposes | 11.01.2017 | 14.15 | [6 empty] | tank bund, island, park, musical fountain, pathway |  | The Kanaka Sarovara (Doddakere) is spread over an area of about 280 acres. It is believed that the saint poet Kanakadasa used to worship Sri Adikeshava after taking a dip in this lake. | 14.699672802161682, 75.34477934229636 | 14.699672802161682 | 75.34477934229636
Varahi Irrigation Project | Irrigation Project | Under Progress | Coastal & Malnad | 15702 |  | Varahi River | ['Udupi'] | ['Kundapur', 'Udupi'] | provide irrigation facility | 27.03.1979 | 9.43 | 20.03.2006 | 569.53 | 1362.38 | 100 | 792.85 |  | ['diversion weir', 'aqueduct'] | [{'name': 'common canal', 'status': 'completed'}, {'name': 'Varahi left bank canal km 0.00 to 30.00', 'status': 'completed'}, {'name': 'Varahi left bank canal km 30.00 to 38.00', 'status': 'nearing completion'}, {'name': 'Varahi left bank canal km 38.00 to 44.35', 'status': 'under progress'}, {'name': 'Varahi right bank canal', 'status': 'yet to start'}] |  | 13.658497954782174, 74.94868452577879 | 13.658497954782174 | 74.94868452577879
Filling of 50 tanks in Harapanahalli taluk | Tank Filling Scheme | Dedicated to Nation | Unknown |  |  | Tungabhadra |  | ['Harapanahalli'] | To lift water from Tungabhadra to fill 50 tanks in drought-prone Harapanahalli taluk | 11.07.2017 | 227 |  |  | 152.36 |  |  |  | 50 tanks |  | Project aims to fill tanks in drought-prone Harapanahalli taluk. | 14.780604907075245, 75.98557448596836 | 14.780604907075245 | 75.98557448596836
Madluru Tank Filling Scheme | Tank Filling Scheme | Completed | Central Karnataka |  |  | Varada | ['Haveri'] | ['Hirekerur', 'Byadagi', 'Hanagal'] | filling 13 tanks of Hirekerur taluk and 2 tanks of Byadagi taluk in Haveri district to 50% of their capacity | 19.10.2017 | 38 |  |  | 29.79 |  |  |  | ['Jackwell', 'Pumphouse', 'Honkana barrage'] |  | Project envisages filling 13 tanks of Hirekerur taluk and 2 tanks of Byadagi taluk in Haveri district to 50% of their capacity by lifting water from the river Varada. Jackwell and Pumphouse constructed at the upper part of Honkana barrage near Thiluvalli village of Hanagal taluk. | 15.044212295350246, 75.74832236912111 | 15.044212295350246 | 75.74832236912111
Filling of 17 tanks in Asundi and adjoining areas | Lift Irrigation Scheme, Tank Filling Scheme | Dedicated to Nation | Central Karnataka |  |  | Kumadwathi River | ['Haveri'] | ['Ranebennur', 'Byadagi', 'Hirekerur'] | Tank Filling | 14.12.2017 | 79.8 |  |  | 76.96 |  |  |  | Asundi LIS, 17 tanks |  |  | 15.746513572020065, 75.02243754847505 | 15.746513572020065 | 75.02243754847505
Filling of 32 tanks of Banavasi Hobli in Sirsi taluk, Uttar Kannada district | Tank Filling Scheme | Dedicated to Nation | Other Regions |  | 0.107 | Varada River | ['Uttar Kannada'] | ['Sirsi'] | To fill 32 tanks to address water shortage for dependent farmers and due to dry borewells | 26.12.2017 | 62.58 |  |  | 19.01 |  |  |  | Lift irrigation system, 32 tanks |  | Project initiated due to shortage of inflow of water to tanks and borewells going dry in the region, causing water shortage for dependent farmers. | 14.533536201183239, 75.01667672293812 | 14.533536201183239 | 75.01667672293812
Hosahalli Tank Filling Scheme | Tank Filling Scheme | Completed | Coastal & Malnad |  |  |  | ['Shivamogga'] | ['Shivamogga', 'Shikaripura', 'Shiralkoppa'] | Solve the drinking water problem of the area by filling these tanks to 50% of their storage capacity, assist in ground water recharge and providing drinking water facility to towns of Shikarpura & Shiralkoppa taluk and surrounding villages. | 01.08.2019 | 250 |  |  | 202.37 |  |  |  | 75 tanks, Anjanapura reservoir |  | Due to reduction in inflow over the years to 75 tanks of Shivamogga taluk and Anjanapura reservoir in Shikaripura taluk, there is a severe stress for drinking water in the area. | 12.995891547707728, 77.47924436265251 | 12.995891547707728 | 77.47924436265251
Mudi Tank Filling Scheme | Tank Filling Scheme | Dedicated to Nation | Unknown |  | 0.35 | Varada River |  | ['Soraba taluk'] | Solving drinking water problem and ground water recharge | 23.08.2019 | 285 |  |  | 215.21 |  |  |  | 66 MI / ZP tanks |  | Filling tanks to 50% of their storage capacity; Water lifted during 3 months in monsoon season. | 14.38081051493438, 75.10193810655439 | 14.38081051493438 | 75.10193810655439
Filling of 186 MI / ZP tanks in Udugani-Talagunda-Hosuru hoblis | Tank Filling Scheme | Under Progress | Unknown |  | 1.53 | Tungabhadra River |  | ['Shikaripura taluk'] | To solve the drinking water problem and assist in ground water recharge by filling tanks to 50% of their storage capacity. | 07.09.2019 | 850 | [6 empty] | ['Lift Irrigation Scheme (LIS)', '186 MI / ZP tanks'] |  | Project addresses severe stress for drinking water due to reduction in inflow to tanks. Water is proposed to be lifted from Tungabhadra River near Puradakere village of Hierkerur taluk during 04 months in monsoon season. Works of LIS are completed and dedicated to the nation, while tank improvement works are under progress. Tanks are located in Udugani-Talagunda-Hosuru hoblis. | 14.265505124321269, 75.35470966492919 | 14.265505124321269 | 75.35470966492919
Filling of 46 (total 53) MI / ZP tanks in Jagalur taluk | Tank Filling Scheme | Under Progress | Unknown |  | 1.37 | Tungabhadra River |  | ['Jagalur taluk'] | Solve the drinking water problem and assist in ground water recharge by filling tanks to 50% of their storage capacity | 07.09.2019 | 660 |  |  | 677.07 |  |  |  | 53 MI / ZP tanks |  | Due to reduction in inflow to the tanks in Jagalur taluk over the years there is a severe stress for drinking water in the area. Water is lifted from Tungabhadra River near Dituru village of Harihara taluk. | 14.519779627832746, 76.33824337116006 | 14.519779627832746 | 76.33824337116006
Filling of 38 tanks in Bharamasagara Hobli and 01 tank in Davanagere taluk | Tank Filling Scheme | Completed | Other Regions |  | 0.514 | Tungabhadra River | ['Davanagere'] | ['Bharamasagara Hobli', 'Davanagere taluk', 'Harihara taluk'] | Solving drinking water problem and assisting in ground water recharge by filling tanks | 01.09.2019 | 565 |  |  | 683.79 |  |  |  | 39 MI / ZP tanks |  | Tanks to be filled to 50% of their storage capacity. Project aims to address severe drinking water stress due to reduced inflow. | 14.463505334612274, 75.92693683865514 | 14.463505334612274 | 75.92693683865514
Anur Tank Filling Scheme | Tank Filling Scheme | Dedicated to Nation | Central Karnataka |  | 0.5 | Tungabhadra River | ['Haveri'] | ['Byadagi'] | Solve drinking water problem and assist in ground water recharge by filling tanks to 50% of their storage capacity. | 01.10.2019 | 212 |  |  | 239.02 |  |  |  | 30 tanks |  | Project involves lifting water from Tungabhadra River near Choudanapura village to fill 30 tanks in 18 villages of Byadagi taluk. Addresses severe drinking water stress due to reduced inflow. | 14.589417165122548, 75.46350338254219 | 14.589417165122548 | 75.46350338254219
Budappanahalli Tank Filling Scheme | Tank Filling Scheme | Dedicated to Nation | Central Karnataka |  | 0.3 | Tungabhadra River | ['Haveri'] | ['Byadagi'] | Solve drinking water problem and assist in ground water recharge by filling tanks to 50% capacity. | 01.10.2019 | 157 |  |  | 158.12 |  |  |  | 17 tanks |  | Project addresses severe stress for drinking water due to reduced inflow to tanks. Water lifted from Tungabhadra River near Kotihal village. | 14.714736677323494, 75.57501933392783 | 14.714736677323494 | 75.57501933392783
Balambeedu Tank Filling Scheme | Tank Filling Scheme | Under Progress | Central Karnataka |  |  | Varada River | ['Haveri'] | ['Hanagal'] | Solve drinking water problem by filling tanks to 50% of their storage capacity and assist in ground water recharge | 01.10.2019 | 386.55 |  |  | 366.79 |  |  |  | 162 Tanks, Pumping infrastructure |  | Project aims to fill 162 tanks in Hanagal taluk to 50% of their storage capacity. | 14.759524020549536, 75.21792268608164 | 14.759524020549536 | 75.21792268608164
Hirekoushi Tank Filling Scheme | Tank Filling Scheme | Completed | Central Karnataka |  |  | Varada River | ['Haveri'] | ['Hanagal'] | Solving drinking water problem and ground water recharge | 01.10.2019 | 117.55 | [6 empty] | Lift scheme infrastructure, 77 tanks |  | Project aims to fill 77 tanks to 50% of their storage capacity. Expenditure of 113.33 Crores incurred as of end of Mar-2023. Addresses severe stress for drinking water due to reduction in inflow to tanks. | 14.649362498268369, 75.1212024677627 | 14.649362498268369 | 75.1212024677627
Sarvagna Tank Filling Scheme | Tank Filling Scheme | Under Progress | Central Karnataka |  | 0.417 | Tungabhadra River | ['Haveri'] | ['Hirekerur', 'Rattihalli'] | Drinking water supply and ground water recharge | 2019-10-01 | 185 |  |  | 88.09 |  |  |  | Tanks |  | Project aims to fill 77 tanks to 50% of their storage capacity. Addresses severe stress for drinking water due to reduction in inflow over the years. | 14.795608117397373, 75.39994232286952 | 14.795608117397373 | 75.39994232286952
Sowkuru Lift Irrigation Scheme | Lift Irrigation Scheme | Dedicated to Nation | Coastal & Malnad | 1350 | 0.589 | Varhi River | ['Udupi'] | ['Kundapur'] | Irrigation | 01.08.2019 | 73.71 |  |  | 67.66 |  |  |  | Salt Water Exclusion Dam |  | Project provides irrigation to Sowkuru, Karkunje, Kenchanooru, Devalakundkanyana and surrounding villages. Water is lifted near Sowkuru village on the upstream side of Salt Water Exclusion Dam constructed across Varhi River near Balkur village. | 13.64631103693205, 74.75642412045393 | 13.64631103693205 | 74.75642412045393
Yennehole Lift Irrigation Scheme | Lift Irrigation Scheme | Dedicated to Nation | Coastal & Malnad | 1500 |  |  | ['Udupi'] | ['Karkala'] | irrigation |  | 108 |  |  | 92.16 |  |  |  | vented dam |  | Benefitting villages: Ajekar, Marne, Koranjibailu, Bolthottu, Higana, Devese, Mundhal, Hermade. Dam constructed near Ajekar village. | 13.213331568400092, 74.99913123579066 | 13.213331568400092 | 74.99913123579066
Kasaba (Kalluwadduhalla) LIS | Lift Irrigation Scheme | Dedicated to Nation | Unknown | 3430 |  | Kumudwathi |  | ['Shikaripura taluk', 'Soraba taluk'] | Provide irrigation and fill tanks | 01.08.2019 | 125.17 |  |  | 131.14 |  |  |  | Lift system, 17 tanks |  | Project aims to fill 17 tanks in Kasaba hobli. | 14.42422558470481, 75.51341658925575 | 14.42422558470481 | 75.51341658925575
Benakanahalli Tank Filling Scheme | Tank Filling Scheme | Under Progress | Other Regions |  |  | Tungabhadra River | ['Davanagere'] | ['Honnali'] | To solve drinking water problem and assist in ground water recharge |  | 48 |  |  | 35.18 |  |  |  | 19 tanks |  | Due to reduction in inflow to tanks, there is severe stress for drinking water. The project aims to fill 19 tanks to 50% of their storage capacity. | 13.886271042711238, 76.30957945304397 | 13.886271042711238 | 76.30957945304397
Govinakov Tank Filling Scheme | Tank Filling Scheme | Under Progress | Other Regions |  | 0.575 | Tungabhadra River | ['Davanagere'] | ['Honnali'] | To solve drinking water problem and assist in ground water recharge by filling tanks. | 01.06.2021 | 415 |  |  | 408.15 |  |  | 386.43 | 94 tanks |  | Water is proposed to be lifted during 120 days of monsoon. Addresses severe stress for drinking water due to reduced inflow. | 15.459442656722965, 76.65492756020502 | 15.459442656722965 | 76.65492756020502
Belthangadi Lift Irrigation Scheme | Lift Irrigation Scheme | Under Progress | Coastal & Malnad | 1100 |  | Nethravathi River | ['Dakshina Kannada'] | ['Belthangadi'] | Provide drinking water, provide irrigation, strengthen river banks, flood protection | 01.06.2021 | 240 |  |  | 64.6 |  |  |  | bridge cum barrage across Nethravathi River |  | Works for the first package of Rs. 173.78 crores are under progress, while works for the second package are under tender process. | 12.903125864714807, 75.07936207736005 | 12.903125864714807 | 75.07936207736005
Holeanveri-Medleri Tank Filling Scheme | Tank Filling Scheme | Under Progress | Central Karnataka |  | 0.263 | Tungabhadra River | ['Haveri'] | ['Ranebennur'] | Solving drinking water problem, ground water recharge, tank filling | 01.06.2021 | 206 |  |  | 33.54 |  |  |  | ['18 tanks', '5 barrages', 'jackwell'] |  | Project involves two phases of water lifting from Tungabhadra River (0.161 TMC for 18 tanks and 5 barrages; 0.102 TMC for Medleri and Rahutanakatte tanks via a jackwell near Medleri village). Tanks to be filled to 50% of their storage capacity. | 14.51206796240738, 75.69095968174271 | 14.51206796240738 | 75.69095968174271
Bullapura-Haade Tank Filling Scheme | Tank Filling Scheme | Under Progress | Central Karnataka |  |  | Tungabhadra River | ['Haveri'] | ['Rattihalli'] | Solving drinking water problem | 01.08.2021 | 24 | [6 empty] | BullapuraHaade and seven other tanks |  | Scheme involves lifting water from Tungabhadra River during monsoon near Biranapada village to fill tanks due to reduced inflow and severe drinking water stress. | 14.422351831211671, 75.51171542337329 | 14.422351831211671 | 75.51171542337329
Swarna LIS | Lift Irrigation Scheme, Barrage Construction, Drinking Water Scheme, Tank Filling Scheme | Yet to Start | Coastal & Malnad | 1000 |  | Swarna River | ['Udupi'] |  | To mitigate severe drinking water stress, rejuvenate and recharge ground water, fill nearby tanks, and irrigate agricultural land. | 01.05.2022 | 165 | [6 empty] | A bridge cum barrage/Salt water extrusion dam across Swarna River near Uppuru village, two bridge-cum-barrages near Parari and Havanje villages |  | Project aims to address severe stress for drinking water due to reduction in ground water levels and insufficient rainfall in Uppuru, Parari, Havanje, Shivalli, Herga, Aruru and other villages. | 13.34681641639635, 74.71282225913704 | 13.34681641639635 | 74.71282225913704
Siddapura LIS | Lift Irrigation Scheme | Yet to Start | Coastal & Malnad | 1200 |  | Varahi | ['Udupi'] | ['Kundapura'] | Irrigation | 01.09.2022 | 165.5 | [6 empty] | Lift Irrigation System | Varahi right bank canal | Benefitting Siddapura, Amparu, Ajri Mutthukodladi villages. Tender process completed. | 13.342080220575681, 74.74786763244656 | 13.342080220575681 | 74.74786763244656
Bennithora Modernisation Works | Modernisation | Nearing Completion | Other Regions | 20234 | 5.75 | Bennithora River | ['Kalaburgi'] | ['Chittapur'] | Irrigation | [8 empty] | ['Bennithora dam', 'Embankment', 'Spillway'] | two canals | Water is being stored since 2001. | 17.44422806481591, 77.02145680253592 | 17.44422806481591 | 77.02145680253592
Bhima Lift Irrigation Scheme | Lift Irrigation Scheme | Nearing Completion | Other Regions | 24292 |  |  | ['Kalaburgi'] | ['Afzalpur'] | Irrigation |  |  |  |  | 1155.5 |  |  |  | barrage |  | Barrage constructed near Sonna village. | 17.17615263920732, 76.3498859251734 | 17.17615263920732 | 76.3498859251734
Gandorinala Modernisation Project | Modernisation | Under Progress | Other Regions | 7943 | 1.99 |  | ['Kalburgi'] | ['Kalburgi'] | Irrigation |  |  |  |  | 98.08 |  |  |  | Dam | Main canal | The main canal of the project was constructed 15 years ago and some parts are dilapidated. Estimated cost for modernisation is Rs.92.00 crores. | 17.32638327529, 76.83530440891488 | 17.32638327529 | 76.83530440891488
Modernisation of Canal Network of Lower Mullamari Project | Modernisation | Under Progress | Other Regions | 9713 | 2.61 | Mullamari | ['Kalaburgi'] | ['Chincholi'] | Modernisation of irrigation infrastructure |  | 117 | [6 empty] | Dam (constructed in 1972) | Canal Network of Lower Mullamari Project | Original dam constructed in 1972 across river Mullamari. Original project provided irrigation to 9713 ha utilising 2.61 TMC of water. Parts of the original project reached dilapidated stage. | 17.539614837364812, 77.23905178206941 | 17.539614837364812 | 77.23905178206941
Amarja Project | Irrigation Scheme | Completed | Hyderabad-Karnataka | 8729 | 1.554 | Amarja River | ['Kalaburagi'] | ['Alanda', 'Afzalpur'] | Irrigation | [8 empty] | Dam |  | Dam constructed near Sangolgi village in Aland Taluk. Target irrigation facility for 8903 ha of land. | 17.486262140609075, 76.55254819274293 | 17.486262140609075 | 76.55254819274293
Bori LIS | Lift Irrigation Scheme | Under Progress | Other Regions |  | 1 | Bori River | ['Kalburagi District'] | ['Alnad', 'Afzalpur'] | Addressing drinking water stress by augmenting water levels in reservoirs and tanks | 01.02.2018 | 450 |  |  | 205.75 |  |  |  | ['Lift Irrigation System', 'Amarja reservoir', '10 MI tanks in Afzalpur taluk', '3 MI tanks in Aland taluk'] |  | Scheme aims to address severe drinking water stress caused by scanty rainfall and reduced water levels in borewells, open wells and tanks in Kalburagi District. Water is lifted near Balundagi village from Bori River, a tributary of Bhima River. | 17.171816575045096, 76.30382352909945 | 17.171816575045096 | 76.30382352909945
Filling of 8 tanks in Aland Taluka from Bori River | Tank Filling Scheme | Yet to Start | Unknown |  |  | Bori River |  | ['Aland'] | Tank Filling |  | 49.5 | [6 empty] | ['8 tanks', 'Bleeder from Bori LIS'] |  |  | 17.17226760019616, 76.30408102115204 | 17.17226760019616 | 76.30408102115204
Karanja Project |  | Nearing Completion | Hyderabad-Karnataka | 29227 |  |  | ['Bidar'] | ['Bhalki', 'Bidar', 'Humnabad'] | Irrigation |  |  |  |  | 890.81 | [6 empty] | 18.103219001061873, 77.07011989808204 | 18.103219001061873 | 77.07011989808204
Modernisation works of Karanja Canals | Modernisation | Nearing Completion | Hyderabad-Karnataka | 29227 |  |  | ['Bidar'] | ['Bhalki', 'Bidar', 'Humnabad'] | Modernisation of canals to provide irrigation facility, especially to tail end areas, due to dilapidated state of existing canals. |  | 482 |  |  | 427.78 |  |  |  | Dam near Byalahalli village, main canal | Karanja Canals, main canal | The main canal was constructed about 30 years ago and reached a dilapidated state, making it difficult to provide water to the tail end. DPR administratively approved in Nov-2017. | 17.909840465860203, 77.52424373478514 | 17.909840465860203 | 77.52424373478514
Supplemental project of providing water from Manikeshwara and Halahalli Barrage between km 60 to 90 of Right Bank Canal to make good the shortage in the inflow of Karanja Reservoir | Supplemental Irrigation Project | Nearing Completion | Hyderabad-Karnataka | 29227 |  |  | ['Bidar'] | ['Bhalki', 'Bidar', 'Humnabad'] | To make good the shortage in the inflow of Karanja Reservoir |  | 126.85 |  |  | 184.71 |  |  |  | ['Manikeshwara Barrage', 'Halahalli Barrage', 'Right Bank Canal', 'Karanja Reservoir'] | Right Bank Canal (km 60-90) | The Karanja Irrigation Project, which this supplemental project supports, has been constructed near Byalahalli village of Bhalki taluk in Bidar district. | 18.043820583586673, 77.2418474202127 | 18.043820583586673 | 77.2418474202127
Upper Mullamari Modernisation Works | Modernisation | Completed | Hyderabad-Karnataka | 3279 |  | Mullamari River | ['Bidar', 'Kalaburgi'] | ['Humnabad', 'Basavakalyana', 'Kalaburgi'] | Modernisation of canal network, create outlet potential |  | 68.6 |  |  | 74.1 |  |  |  | dam, main canal | main canal, canal network | The main canal of the project was constructed 30 years ago and some parts reached a dilapidated state, leading to modernisation works. | 17.768548891264178, 77.1298813428182 | 17.768548891264178 | 77.1298813428182
Filling of Chulkinala Reservoir and tanks by lifting water from Kongali Barrage in Basavakalyana taluk | Tank Filling Scheme, Lift Irrigation Scheme, Drinking Water Scheme | Under Progress | Hyderabad-Karnataka |  | 0.768 | Kongali Barrage | ['Bidar'] | ['Basavakalyana'] | provide drinking water to people and cattle and to replenish ground water resources |  | 188 |  |  | 147.47 |  |  |  | ['Chulkinala Reservoir', 'Kongali Barrage', '15 tanks'] |  | Kongali barrage is near Jamakhandi village. | 18.060136492381645, 76.99128287740679 | 18.060136492381645 | 76.99128287740679
Kagina LIS | Lift Irrigation Scheme | Yet to Start | Other Regions | 1870 |  | Kagina River | ['Kalaburgi'] | ['Chitthapura', 'Chincholi', 'Sedam'] | irrigation facilities |  | 143.8 | [6 empty] | two lift schemes |  | The people in the drought prone Sedam assembly constituency in Chitthapura, Chincholi and Sedam talukas of Kalaburgi district are dependent on Kagina River for their drinking water needs and irrigation purposes. The DPR of the project was administratively approved in Apr-2022. | 17.19058501835457, 77.13612741089432 | 17.19058501835457 | 77.13612741089432
Ainapura LIS | Lift Irrigation Scheme | Tender Process | Unknown | 3710 |  |  |  | ['Chincholi'] | provide irrigation facility | 2023-01-01 | 204.1 | [8 empty] | Benefitting Inapura and 17 other villages of drought prone areas. | 16.811208128939143, 76.49082662351167 | 16.811208128939143 | 76.49082662351167
Filling of 36 tanks by lifting water from Manjra River upstream of Halahalli barrage near Balat (B) village of Aurad Taluk, Bidar District | Tank Filling Scheme, Drinking Water Scheme | Tender Process | Hyderabad-Karnataka |  |  | Manjra River | ['Bidar District'] | ['Aurad Taluk'] | Solve the drinking water problem of the area by filling these tanks to 50% of their storage capacity and also assist in ground water recharge | 2023-01-01 | 560.7 | [6 empty] | Halahalli barrage, 36 tanks |  | DPR administratively approved. Work yet to be started. Action being taken to invite tenders for second stage. | 12.515121520508872, 76.90443671934514 | 12.515121520508872 | 76.90443671934514
Filling of Bennithora Reservoir | Tank Filling Scheme | Tender Process | Other Regions | 20234 | 1.624 | Kagina River | ['Kalaburgi District'] |  | To compensate for drinking water diversion and ensure irrigation facility by filling Bennithora Reservoir |  | 365 | [6 empty] | ['Lift scheme', 'Bennithora Reservoir'] |  | Karnataka Urban Infrastructure Development and Finance Corporation (KUIDFC) has proposed to take up 24/7 drinking water facility to Kalaburgi city by utilizing 1.624 TMC of water from Bennithora Reservoir, causing a shortage of water from irrigation. | 17.443753291020972, 76.99079183970065 | 17.443753291020972 | 76.99079183970065
Mehkar LIS | Lift Irrigation Scheme | Tender Process | Hyderabad-Karnataka | 8475 |  | Manjra River | ['Bidar'] | ['Bhalki'] | Drinking Water and Irrigation | 2023-01-01 | 762 | [6 empty] | Lift Irrigation Scheme |  | Proposed to mitigate severe stress for drinking water and reduction in ground water levels due to reduction in inflow to tanks. Benefits 12 villages. Water lifted from Manjra River upstream of Manikeshwar barrage. | 20.148158421669937, 76.57228194925453 | 20.148158421669937 | 76.57228194925453
Modernisation of Tungabhadra Canal Network | Modernisation | Under Progress | Kalyana Karnataka | 362938 |  | Tungabhadra River | ['Ballari', 'Raichur', 'Koppal'] |  | Modernisation of Irrigation facilities |  |  |  | 3161.35 | 3144.75 | 99.5 | -16.6 |  | ['Tungabhadra Dam', 'Canal Network'] | Tungabhadra Canal Network | The Tungabhadra Project is a multipurpose inter-state project. The original dam and canal works of this project have been completed. The Tungabhadra Dam has been constructed near Mallapur in Hospet taluk of Ballari district. | 15.265256437968791, 76.34973137626326 | 15.265256437968791 | 76.34973137626326
Hirehalla Project | Dam Construction | Completed | Kalyana Karnataka | 8330 |  | Hirehalla | ['Koppal'] | ['Koppal'] | Irrigation |  |  |  |  | 462.7 |  |  |  | Dam |  | R&R works are under progress. | 15.446949763210153, 76.10451805927205 | 15.446949763210153 | 76.10451805927205
Singatalur Lift Irrigation Scheme | Lift Irrigation Scheme | Under Progress | Central Karnataka | 107380 |  |  | ['Bellary', 'Koppal', 'Gadag'] | ['Huvinahadagali', 'Koppal', 'Yalaburgi', 'Gadag', 'Mundargi'] | Irrigation |  |  |  |  | 4045.53 |  |  |  | ['Barrage'] | [{'name': 'Right Bank Canal', 'length_km': 40.13, 'status': 'completed'}, {'name': 'Left Bank Canal', 'length_km': 166.44, 'status': 'under progress'}] | 19,587 ha irrigated through flow and 87,793 ha through Drip. Drip irrigation works for 71074 ha under the 166.44 km long left bank canal are under progress. | 15.0585084743703, 75.88714963743865 | 15.0585084743703 | 75.88714963743865
Modernization Of Vijayanagar Canals | Modernisation | Under Progress | Unknown | 11222 |  |  |  | ['Hospet', 'Ballari', 'Shiraguppa', 'Gangavathi', 'Koppala', 'Manvi'] | Irrigation |  | 456.63 |  |  | 515.18 |  |  |  | Vijayanagara Channel system | Vijayanagara Channel system | The Vijayanagara Channel system was built during the period of Vijayanagara Empire. The works are taken up with loan assistance of the Asian Development Bank. | 15.268554337406217, 76.39298185236711 | 15.268554337406217 | 76.39298185236711
Rajoli Banda Project | Modernisation | Under Progress | Unknown | 2380 |  | Tungabhadra |  |  | Creation of outlet potential for irrigation |  |  |  |  | 52.2 |  |  |  | Tungabhadra reservoir |  | Outlet potential created from water available from the lower basin of Tungabhadra reservoir and from the regenerated water of Tungabhadra project. The main project is completed, and modernization works are under progress. | 15.906627010567316, 78.09011539119344 | 15.906627010567316 | 78.09011539119344
Alvandi Betageri LIS | Lift Irrigation Scheme | Nearing Completion | Unknown | 5992.3 |  |  |  | ['Koppal'] | Provide irrigation facility |  | 87.36 |  |  | 82.33 | [6 empty] | 16.144677163982806, 74.9822892922598 | 16.144677163982806 | 74.9822892922598
Filling of Malvi Reservoir in Hagaribommanahalli taluk of Ballari district by Lift Irrigation from Tungabhadra River | Lift Irrigation Scheme | Nearing Completion | Kalyana Karnataka | 2965 |  | Tungabhadra River | ['Ballari'] | ['Hagaribommanahalli'] | To feed water to Malvi Reservoir by lifting water from Tungabhadra River to make good the shortage of inflow for irrigation purposes. | 01.08.2017 | 144.95 |  |  | 135.82 |  |  |  | ['Malvi Reservoir', 'Lift Irrigation System', 'Dam across Chikahagari River'] |  | An existing dam was constructed in 1972 near Malavi village across the Chikahagari river to provide water for monsoon and post-monsoon crops. Due to reduction in rainfall and construction of small tanks upstream, adequate water is not being stored in the reservoir, leading to the proposal for lift irrigation from Tungabhadra River. | 15.040692587774704, 76.18449649641803 | 15.040692587774704 | 76.18449649641803
Filling of 20 Percolation Tanks by lifting water from Tungabhadra near Itagi village in Shirahatti taluk of Gadag district | Tank Filling Scheme | Under Progress | Central Karnataka |  | 0.226 | Tungabhadra | ['Gadag'] | ['Shirahatti'] | Addressing drinking water shortage for people and cattle, and replenishing depleted groundwater resources | 01.07.2017 | 140 |  |  | 10.3 |  |  |  | 20 Percolation Tanks, Lift System |  |  | 15.232421201664724, 75.5788348157182 | 15.232421201664724 | 75.5788348157182
Thimmapur Lift Irrigation Scheme | Lift Irrigation Scheme | Dedicated to Nation | Kalyana Karnataka | 34984 |  |  | ['Raichur'] | ['Sindhanur'] | stabilisting the suffering tail end atchkat area |  | 92 |  |  | 79.42 |  |  |  |  | ['TLBC Dy.54'] | Near Turakatti village. | 14.955407988074835, 75.72820759907438 | 14.955407988074835 | 75.72820759907438
Filling of Karadona & Ramadurga tanks | ['Tank Filling Scheme', 'Drinking Water Scheme'] | Nearing Completion | Unknown |  |  |  |  | ['Gangavathy'] | To augment the reduction in flow to the tanks of Kanagairi area and ensure adequate drinking water facility in the area. |  | 15 | [6 empty] | ['Kardona Tank', 'Shirwara Tank', 'Ramdurg Tank', 'Hoskere Tank'] |  | Water is proposed to be lifted from the already completed MI scheme â€œDevalapura and Other tank filling schemeâ€ and supplied to Kardona, Shirwara, Ramdurg and Hoskere tanks upto 50% of their storage capacity. | 15.432584881302475, 76.5259412609265 | 15.432584881302475 | 76.5259412609265
Bahaddur Bandi LIS | Lift Irrigation Scheme | Under Progress | Unknown | 5256 | 0.6 | Tungabhadra River |  |  | To financially strengthen the farmers and provide irrigation facility to land suffering from reduced rainfall. |  | 188.41 |  |  | 36.7 | [5 empty] | Project covers Bahaddur Bandi and 18 adjoining villages. Works proposed in two stages. Stage-1 administratively approved for Rs.80.00 crores. | 15.315530967776887, 76.16274123079032 | 15.315530967776887 | 76.16274123079032
Augmentation of Ganekal Balancing Reservoir from Krishna River | Drinking Water Scheme | Dedicated to Nation | Kalyana Karnataka |  | 0.745 | Krishna River | ['Raichur'] | ['Raichur'] | To make good the shortage in drinking water supply to Raichur city and enroute villages due to siltation in Tungabhadra Dam. |  | 189.22 |  |  | 109.77 |  |  |  | ['Ganekal Balancing Reservoir', 'Tungabhadra Dam', 'Gugal barrage'] | Tungabhadra LBC | The Ganekal balancing reservoir was originally filled by the Tungabhadra LBC. Due to siltation in Tungabhadra Dam, it is now proposed to fill the reservoir by lifting water from Gugal barrage across Krishna River. | 15.70168089317547, 77.22249808709587 | 15.70168089317547 | 77.22249808709587
Filling up of 13 tanks and providing drinking water facility to 21 villages in Hospete taluk | Lift Irrigation Scheme, Tank Filling Scheme, Drinking Water Scheme | Tender Process | Unknown |  | 0.223 | Tungabhadra River |  | ['Hospete taluk'] | Tank filling and providing drinking water facility |  | 243.35 |  |  | 205.99 |  |  |  | ['18 tanks (including 03 percolation tanks)', '04 series check dams', 'reservoirs'] |  | Water to be lifted during 03 months of monsoon season. Project benefits mining affected villages. | 15.268388735254172, 76.39263852963032 | 15.268388735254172 | 76.39263852963032
Filling of Aladamma Kere in Sugnahalli village in Bannikoppa Gram Panchayati, Shiratti taluk, Gadag district | Tank Filling Scheme | Under Progress | Central Karnataka |  |  | Tungabhadra River | ['Gadag'] | ['Shiratti'] | To make good the shortage in inflow to these tanks |  | 10 | [6 empty] | ['Aladamma Kere', 'Tanks in Bannikoppa village'] |  |  | 15.256444557257877, 75.66832052309299 | 15.256444557257877 | 75.66832052309299
Mukkumpi Tank Filling Scheme | Tank Filling Scheme | Under Progress | Kalyana Karnataka |  | 0.105 | Tungabhadra River | ['Koppal District'] | ['Gangavathi taluk'] | To make good the shortage in inflow to Mukkumpi tank and 5 other tanks. | 2021-06-01 | 93 |  |  | 15.27 | [6 empty] | 15.420811359254957, 76.39054585422664 | 15.420811359254957 | 76.39054585422664
Kudligi Tank Filling Scheme | Tank Filling Scheme | Under Progress | Unknown |  | 1.441 | Tungabhadra River |  | ['Kudligi'] | Fill 74 tanks in Kudligi constituency | 01.06.2021 | 670 |  |  | 670.66 |  |  | 500 | ['Pump house near Rajawala village', 'Delivery chamber (DC-1) near Nadamannahalli', 'Sunkadakallu tank (balancing Reservoir)'] |  | Involves two stages: Stage 1 lifts water from Tungabhadra River to DC-1 and then to 16 tanks including Sunkadakallu tank via gravity mains. Stage 2 lifts water from Sunkadakallu tank to fill the balance 58 tanks via gravity mains. | 14.905357153868456, 76.39001496850214 | 14.905357153868456 | 76.39001496850214
Jalawadgi Tank Filling Scheme | Tank Filling Scheme | Yet to Start | Central Karnataka |  |  |  | ['Gadag District'] | ['Shirahatti', 'Mundargi'] | solving drinking water problem, ground water recharge | 01.03.2022 | 197.5 | [6 empty] | tanks, check dams |  | Due to reduction in inflow to tanks, severe stress for drinking water. Project aims to fill tanks to 50% of their storage capacity. | 14.904216689290084, 76.38719328475916 | 14.904216689290084 | 76.38719328475916
Maskinala Modernisation | Modernisation | Under Progress | Kalyana Karnataka | 3001 | 0.78 | Maskinala | ['Raichur'] | ['Lingsugur'] | To provide irrigation facility and modernize existing canal infrastructure. |  | 52.54 |  |  | 13.29 |  |  |  | ['Dam', 'Main Canals', 'Distributaries'] | Main canals and distributaries | Original main canals and distributaries were completed 20 years ago and are now in a dilapidated state causing problems in water supply to tail end areas. | 16.018714485062297, 76.5482711741082 | 16.018714485062297 | 76.5482711741082
Indargi Tank Filling Scheme | Tank Filling Scheme | Under Progress | Kalyana Karnataka |  |  | Tungabhadra River | ['Koppal District'] | ['Gangavathi'] | Solve drinking water problem by filling tanks to 50% of their storage capacity and assist in ground water recharge. |  | 241.2 | [6 empty] | Lift scheme from Tungabhadra River, 22 tanks, 6 tanks |  | Project proposes to lift water from Tungabhadra River near Gadmadi village to fill 22 tanks. Another 6 tanks will be filled from Venkatgiri, which is in turn filled under Mukkumpi TFS. The estimate and DTP for the work is under preparation. | 15.441816839981323, 76.32460734086432 | 15.441816839981323 | 76.32460734086432
Gunjalli Tank Filling Scheme | Tank Filling Scheme | Under Progress | Unknown |  |  | Tungabhadra |  | ['Raichur'] | Alleviate drinking water scarcity for people and livestock and increase ground water level |  | 146.8 |  |  | 15.1 |  |  | 146.8 | ['Vaddageri Basappa Lake'] | ['Tungabhadra Left Bank Canal'] | Vaddageri Basappa Lake, dating back 60-65 years, has a present capacity of 0.56 TMC and a length of 2.30 km. It was originally constructed to provide water to about 584-21 acres of Gunjalli village. Water in the lake is currently collected only from rain. Villages facing drinking water problems include Jambaladinni, Puchchaladinni, Yeragera, Midagaladinni, Gunjalli, Idapanur, and Budura. | 15.775806889709008, 76.62747142312493 | 15.775806889709008 | 76.62747142312493
Chikkamanchali BCB | ['Barrage Construction', 'Drinking Water Scheme', 'Eco-Tourism'] | Yet to Start | Kalyana Karnataka |  |  | Tungabhadra river | ['Raichur'] |  | Connecting two holy places (Panchamukhi Anjaneya swamy temple and Mantralaya) for devotees and providing water to people, livestock, farmers, and devotees during the summer season from the backwaters collected in the bridge barrage. | [8 empty] | bridge barrage |  | Administrative approval for Rs.158.10 crores is expected in February-2024, subject to the approval of the State of Andhra Pradesh. Efforts are being made to get the approval of the State of Andhra Pradesh. | 16.213161912882388, 77.35541506041838 | 16.213161912882388 | 77.35541506041838