## Sheet1
Project Name | Hectares of land irrigated | Canals under this project | DRP Approval Date | Approval Amount | Revised Approval | Revised Date | Expenditure | Area | Taluk | District | Latitude | Longitude | Project Status | Lift Scheme
Ghataprabha Project | 3,10,823 Ha proposed; 3,08,326 Ha potential created | GRBC (199 km), Branch Canal (88 km), Distributaries (994 km) | null | null | null | null | null | Athani, Chikkodi, Gokak, Hukkeri, Raibag, Ramdurg, Savadatti, Badami, Bagalkot, Bilagi, Hunagund | Jamakhandi & Mudhol | Belagavi & Bagalkot | 16.1464 | 74.6425 | completed | Daddinaganur LIS Rustumpur LIS Kotabagi LIS
Ghataprabha Left Bank Canal Modernisation | null | main canal of Ghataprabha (selected reaches in 0.00 to 109.00 km), Gokak Canal (0.00 to 20.00 km), Saidapura Canal (0.00 to 24.00 km), South Canal (selected reaches in 0.00 to 45.00 km) and Bilagi Branch Canal (selected reaches in 0.00 to 49.00 km). | null | 573.28 crores | null | null | null | null | null | null | 15.5869 | 76.408 | nearly complete | null
Hippargi Irrigation Project | 74,742 Ha (proposed and achieved) | Main Canal — 306 km | null | null | null | null | null | Athani, Chikkodi | Jamakhandi | Belagavi, Bagalkot | 16.5529 | 75.1546 | completed | Ainapur Stage I & II LIS, Karimasuthi Stage I & II LIS, Halyal Stage I & II LIS, Savalgi–Tunga LIS (all completed)
Markandeya Project | 14,448 Ha (proposed) | Distributary and FIC works under progress | null | null | null | null | null | Belagavi region | Belagavi, Hukkeri, Gokak, Savadatti | Belagavi | 13.9461 | 75.4713 | Nearly Completed (most works completed; distributary/FIC in progress) | null
Murgod Lift Irrigation Scheme | 1,939 Ha | Markandeya Right Bank Canal (from 55th km near Malagali village) | null | null | null | null | null | 8 villages | null | null | 12.983 | 77.5952 | under progress | Lifting scheme from 55th km of Markandeya Right Bank Canal
Chachadi Lift Irrigation Scheme | 2,718 Ha | Markandeya Right Bank Canal (from 34th km) | null | null | null | null | null | null | null | null | 12.982 | 77.5955 | Nearly Completed | Lifting scheme from 34th km of Markandeya Right Bank Canal
Doodhganga Project | 44,766 Ha (Maharashtra), 15,167 Ha (Karnataka) | Nidhori Branch Canal (21.57 km), Bidari Branch Canal (25.155 km), Dattawad Branch Canal (30 km) | null | null | null | null | null | Maharashtra & Karnataka | Rathnagiri (Maharashtra), Karnataka Taluks not specified | Kolhapur (Maharashtra), Karnataka District not specified | 16.5635 | 74.5092 | Nidhori Completed, Bidari Under Progress | null
Bellary Nala Project | 8,200 Ha | Main Canal — 106 km (works from km 44–106 under progress; km 1–10 & 32–40 in forest excluded) | null | null | null | null | null | null | Belagavi, Gokak, Saundatti, Bailahongal | Belagavi | 15.8397 | 74.5439 | nearly completed | null
Sri Rameshwara Lift Irrigation Scheme | Sri Rameshwara Lift Irrigation Scheme | null | null | null | null | null | null | null | Ramadurga, Savadatti, Gokak | Belagavi | 15.8475 | 74.4823 | Completed (FIC works under progress) | Utilises 2.2 TMC water from Ghataprabha River
Kinaye Project | 1,200 Ha (Khariff), 275 Ha (Rabi) | Canal network (under progress) | null | null | null | null | null | null | null | Belagavi | 15.7941 | 74.4842 | under progress | Dam across Mangothri River
Tubachi – Babaleshwar Lift Irrigation Scheme | 52,700 Ha | Main Canal & distributaries (Phase-II under progress),Intake Canal Kavatagi Sub Station West Canal at Ch.15.900 km Jackwell cum Pump house West Canal Aqueduct at Ch.4.32 km West Canal at Ch.19.200 km | null | Rs. 3572.00 crores | null | null | null | Vijayapur region | Vijayapur, Athani, Jamakhandi | Belagavi & Bagalkot | 16.6158 | 75.2746 | Phase-I nearing completion; Phase-II under progress | Utilises 6.30 TMC water from Krishna River
Basaveshwar (Kempwad) Lift Irrigation Scheme | 27,462 Ha | null | null | Rs. 1120.36 crores | null | null | null | Northern part of Athani Taluk | Athani | Belagavi | 16.758 | 74.8958 | under progress | Utilises 4.00 TMC water from backwaters of Hipparagi Barrage near Ainapur village
Sri Veerabhadreshwar Lift Irrigation Scheme | 17,377 Ha | null | null | Rs. 544.00 crores | null | null | null | null | Mudhol, Ramdurga | null | 15.1737 | 75.6475 | under progress | Lifting 2.50 TMC water from Ghataprabha River & filling 10 minor tanks
Venkateshwar Lift Irrigation Scheme | 7,200 Ha | null | null | Rs. 174.42 crores | null | null | null | 10 villages (4 Mudhol, 6 Jamakhandi) | Mudhol, Jamakhandi | null | 15.1155 | 76.0305 | under progress | null
Improvements to Chikkodi Branch Canal | 11,481 Ha (proposed improvements); 33,403 Ha (existing) | Chikkodi Branch Canal — 88 km (first 30 km improvements) | null | null | null | null | null | null | null | null | 16.427 | 74.5706 | Nearly Completed | null
Sultanpur Bridge Cum Bandhara Construction | null | null | 2017-02-01 | Rs. 19.52 crores | null | null | null | Sultanpur village | Hukkeri | Hukkeri | 16.2327 | 74.5989 | Completed | null
Filling of 17 tanks of 10 villages and additional 22 tanks of Raibag Taluk | null | null | null | Rs. 91.40 crores | null | null | null | 10 villages + 22 additional tanks | Raibag | Belagavi | 16.494 | 74.7784 | Under Progress | Filling tanks from Krishna River to 50% capacity & assist groundwater recharge
Filling of 19 tanks of 10 villages of Kudachi constituency | null | null | null | Rs. 34.38 crores | null | null | null | 10 villages | Raibag | Belagavi | 16.627 | 74.8522 | Under Progress | Filling tanks from Krishna River to 50% capacity & assist groundwater recharge
Kullahalli Hunnur LIS | 9,163.63 Ha | Jamakhandi Branch Canal (starts at km 70, Chimmad Chowki of GLBC) | null | Rs. 73.75 crores | null | null | null | Downstream Jamakhandi & surrounding villages | Jamakhandi | Belagavi | 16.5274 | 75.1823 | Under Progress | Lifting 0.88 TMC water from Krishna River
Godchinamalki LIS | 1,031.51 Ha (Stage-I), 1,537.91 Ha (Stage-II), Total 2,568.42 Ha | null | 2018-01-01 | Rs. 107.16 crores | null | null | null | 12 villages | Gokak | Belagavi | 16.1266 | 74.7471 | Under Progress | Stage-I: 0.191 TMC from Ghataprabha River; Stage-II: 0.280 TMC from Markandeya River
Strengthening and Raising of Galgali Barrage | 7,448 acres (~3,016 Ha) | null | null | null | null | null | null | null | Bilagi | Bagalkot | 16.4238 | 75.4382 | Under Progress | Increase storage capacity from 0.569 TMC to 1.244 TMC; caters irrigation & drinking water
Salapura LIS | Total 13,000 Ha (10,878 Ha in Ramadurga, 1,832 Ha in Badami, 290 Ha in Mudhol) | null | 2018-03-01 | Rs. 566 crores | Stage-wise: Rs. 327 crores & Rs. 239 crores | null | null | 19 + 6 + 2 villages | Ramadurga, Badami, Mudhol | Bagalkot | 13.3817 | 76.1703 | Stage-I under progress | Lifting water from Ghataprabha River near Chikkur Thanda, Mudhol Taluk
Kittur Tank Filling Scheme | null | null | 2017-11-01 | Rs. 248.20 crores | null | null | null | 64 tanks | Kittur & Bailhongal Constituency | Belagavi | 15.597 | 74.7858 | Under Progress | Filling tanks to 50% capacity to solve drinking water problem & assist groundwater recharge
Malaprabha Project | 1,96,132 Ha | null | null | null | null | null | null | null | Saundatti | Belagavi, Dharwad, Gadag, Bagalkot | 16.1683 | 74.8453 | Dam & Canal works completed; FIC works under progress | null
Modernisation of Malaprabha Main Canal and Distributaries | null | Malaprabha Main Canal & selected reaches of distributaries | Oct-2019 (2nd stage approval) | Rs. 1,120 crores (1st stage), Rs. 1,000 crores (2nd stage) | null | null | null | null | null | null | 16.0779 | 74.767 | 1st stage: nearing completion; 2nd stage: works started | null
Amargol LIS and Gobbargumpi LIS | 1,696 Ha (Amargol) + 2,160 Ha (Gobbargumpi), Total 3,856 Ha | Sub Distributary 17L & D-6 Distributary of Nargund Branch Canal | null | Rs. 48.08 crores | null | null | null | Last part of Sub Distributaries 17L & D-6 | Nargund | null | 15.6054 | 75.3495 | Completed | Lifting water from Bennehalla (Amargol) & Tupparihalla (Gobbargumpi)
Kalasa Nala and Bandura Nala Diversion Project | null | null | Gazette 27-02-2020 | null | null | null | null | null | null | null | 13.2334 | 75.3544 | DPR prepared; works pending clearance | Kalasa Nala: 1.72 TMC to Malaprabha River; Bandura Nala: 2.18 TMC to Malaprabha River
Shiggaon Lift Irrigation Scheme | 9,900 Ha (sprinkler) + 3,600 Ha (drip), Total 13,500 Ha | null | null | null | null | null | null | 18 + 39 tanks | Shiggaon, Savanur, Hanagal | Haveri | 15.4363 | 75.0285 | Partially completed; scheme dedicated to the nation | Sprinkler irrigation for 9,900 Ha completed; filling 18 tanks completed, 39 tanks under progress
Savanur Lift Irrigation Scheme | 15,500 Ha | null | null | null | null | null | null | 30 villages + 48 MI tanks | Savanur | Haveri | 14.972 | 75.3437 | Under Progress | Lifting 1.5 TMC water from Varada River near Kalasuru; Head works nearing completion
Modernisation of Kolachi Right Bank Canal | 5,877 Ha | Kolachi Right Bank Canal (49 km) | null | null | null | null | null | null | Ramadurga | Belagavi | 15.9358 | 75.3522 | Partially completed; 4 out of 5 packages done | null
Filling of tanks in Siddhanabhavi, Bendageri and Muthnal villages | null | null | 2017-03-01 | Rs. 12.57 crores | null | null | null | Tanks in 3 villages | Belagavi | Belagavi | 16.2101 | 74.702 | Under Progress | Lifting 0.0285 TMC water from Malaprabha River near Parishwad village
Filling of tanks from Tuparihalla | null | null | 2017-03-01 | Rs. 22.50 crores | null | null | null | MI tanks in Tadakoda, Bhokyapura, Garaga, Halethegooru, Bogooru, Neeralakatti | Dharwad | Dharwad | 15.5809 | 74.9257 | Under Progress | Lifting 0.164 TMC water from Tuparihalla
Filling of tanks and bandharas of Haliyala taluk | null | null | null | Rs. 220.00 crores | null | null | null | 46 tanks & 19 barrages | Haliyal | Uttara Kannada | 15.3299 | 74.7655 | Under Progress | Lifting 0.812 TMC water from Kali River
Filling of MI tanks of Kalaghatagi taluk | null | null | null | Rs. 125.00 crores | null | null | null | 35 tanks | Kalaghatagi | Dharwad | 15.1816 | 74.9711 | Under Progress | Lifting 0.449 TMC water from Bedti River
Filling of 129 tanks in Mundgod taluk | null | null | null | null | null | null | null | 129 tanks | Mundgod | Uttara Kannada | 14.9747 | 75.0403 | Under Progress | Lifting 1.48 TMC water from Bedti River during rainy season
Filling of 84 tanks in 05 Gram-Panchayats of Mundgod taluk | null | null | 2019-10-01 | Rs. 225.00 crores | null | null | null | 84 MI/ZP tanks in Malagi, Phala, Katturu, Khodambi, Onnikeri | Mundgod | Uttara Kannada | 14.9733 | 75.0389 | Under Progress | Lifting 0.2 TMC water from Kavalagi halla (distributary of Bedti River)
Bagewadi Tank Filling Scheme | null | null | 2019-01-01 | Rs. 379.92 crores | null | null | null | 62 tanks, 47 villages | Belagavi Rural | Belagavi | 16.5713 | 75.9772 | Under Progress | Lifting 0.469 TMC water from Malaprabha River near Hirehattiholi
Hingaragi Tank Filling Scheme | null | null | null | Rs. 143.53 crores | null | null | null | 13 tanks | Belagavi | Belagavi | 15.8435 | 74.4995 | Under Preparation | Lifting 0.175 TMC water from Markandeya River
Upper Tunga Project | 80,494 Ha | Upper Tunga Main Canal — 258 km; 6 distributories | null | null | null | null | null | 258 km main canal, 6 distributories | Shimoga | Davanagere, Shivamogga, Haveri | 13.7308 | 75.4887 | Nearly Completed | Main Canal: 230 km completed; Dy.6 distributory works pending
Modernisation of Tunga Anicut | null | Left & Right Bank Canal of Tunga Anicut; Package-1 (0-32 km), Package-2 (32 km to tail end), LBC km 21.79–21.92 km | null | null | null | null | null | null | Shimoga | Davanagere, Shivamogga, Haveri | 13.8329 | 75.4372 | Under Progress | Modernisation works including Dy.2 Ch.50+100 km aqueduct, LBC km 21.79–21.92 km
Basapura Lift Irrigation Scheme | 2000 Ha | null | null | null | null | null | null | 13 villages | Hangal | Haveri | 12.8416 | 77.6145 | Completed | Lifting 0.6 TMC from Varada River in two stages; Jackwell cum pumphouse, 1st Stage Delivery Chamber
Ubrani-Amruthapura Lift Irrigation Scheme | null | null | null | null | null | null | null | 146 tanks (89 Channagiri, 57 Tarikere) | Channagiri & Tarikere | Davanagere & Chikkamagaluru | 13.7417 | 75.8537 | Partially Completed / Commissioned | Pumping Machinery (3+1), Delivery Chamber Head Regulator, 2-stage tank filling; pipeline extension ongoing
Development of Canals of Ambligola and Anjanapura Project | 7,908–13 acres (Ambligola), 6736 Ha (Anjanapura) | Canal development works | null | Rs.38.00 crores (estimated) | null | null | null | null | Shikaripura | Shimoga | 13.0486 | 77.5789 | Nearly Completed | null
Kachavi Tank Filling Scheme | null | null | null | Rs.16.50 crores | null | null | null | 21 tanks in 11 villages | Soraba | Shimoga | 14.5807 | 75.0855 | Under Progress | Lifting 0.15 TMC from Varada River to fill tanks
Dharma Modernisation | 7692 Ha | null | null | null | null | null | null | Yemgalli | Mundagod | Uttara Kannada | 15.0331 | 75.0022 | Completed | Modernisation works completed
Bhadra Canal Network Modernisation | 105,570 Ha | Bhadra Canal System (modernisation of unlined canals) | null | null | null | null | null | null | Chikkamagalur, Davangere, Shivamogga | Chikkamagalur, Davangere, Shivamogga | 14.3942 | 76.0027 | Most works completed; remaining works in progress | Modernisation of canals
Gondi Canal Network Modernisation | 4600 Ha | Gondi Canal System (modernisation of unlined canals) | null | null | null | null | null | null | null | Shivamogga | 13.7364 | 75.4116 | Completed (Dec-2019) | Modernisation of canals
Hodirayanahalla Diversion Scheme | 1,296 Ha (existing) + 243 Ha (new) | Diversion from Hodirayanahalla to Jambadahalla Reservoir | null | null | null | null | null | Jambadahalla | null | null | 13.6739 | 75.7592 | Completed | Diversion scheme
Rajanahalli Lift Irrigation Scheme | null | Lifting water from Tungabhadra River to fill 22 tanks; extended to additional tanks | null | Rs.14.50 crores (extension) | null | null | null | Davanagere, Jagaluru, Harapanahalli, Chithradurga | Harihara, Chithradurga | Davanagere, Chithradurga | 14.5086 | 75.7607 | Completed; weir construction nearing completion | null
Development of Kanaka Sarovara (Doddakere) in Kaginele village | null | null | null | Rs.14.15 crores | null | null | null | Kaginele | null | null |  |  | Under Progress | null
Varahi Irrigation Project | 15,702 ha | null | null | null | null | null | null | 33 villages (Kundapur taluk) and 35 villages (Udupi taluk) | Kundapur, Udupi | Udupi | 13.6574 | 74.9476 | under progress | null
Sasvehalli Tank Filling Scheme | null | null | null | Rs.415.68 crores | null | null | null | Filling 27 tanks (Channagiri), 11 (Mayakonda), 4 (Honnali), 1 (Shivamogga Rural) in Stage I; 24 (Santebennur), 19 (Mayakonda), 3 (Chitradurga), 3 (Holalkere) in Stage II | Channagiri, Davanagere, Honnali, Shivamogga, Chitradurga, Holalkere | Davanagere, Shivamogga, Chitradurga | 14.1617 | 75.7148 | under progress | 2-stage Lift Irrigation Scheme
Filling of Ranebennur Doddakere and other 03 tanks | null | null | 2017-07-01 | Rs.31.00 crores | null | null | null | Filling of 4 tanks including Ranebennur Doddakere | Ranebennur | Haveri | 14.269 | 75.3394 | under progress | null
Filling of 50 Tanks in Harapanahalli Taluk | null | null | 2017-07-01 | Rs.227.00 crores | null | null | null | Filling of 50 tanks from Tungabhadra River near Chikkabidare village | Harapanahalli | Davanagere | 14.7823 | 75.9918 | under progress | null
Filling of Durgadevi and Bahugrama Tanks of Hirekerur Town by Lifting Kumadwathi Water from Madaga Masuru Tank | null | null | 2017-10-01 | Rs.140.00 crores | null | null | null | Filling of 8 tanks including Durgadevi and adjoining tanks in Hirekerur town | Hirekerur | Haveri | 14.4596 | 75.3981 | under progress | Lift from River Kumadwathi via Jackwell & Pumphouse at Thippayikoppa village
Madluru Tank Filling Scheme | null | null | 2017-10-01 | Rs.38.00 crores | null | null | null | Filling of 15 tanks (13 in Hirekerur taluk and 2 in Byadagi taluk) | Hirekerur, Byadagi | Haveri | 15.8825 | 75.0527 | under progress | Lift from River Varada via Jackwell & Pumphouse near Thiluvalli village, Hanagal taluk
Guddadamadapura Tank Filling Scheme | null | null | 2018-02-01 | Rs.23.00 crores | null | null | null | Filling of 13 tanks | Hirekerur | Haveri | 14.3132 | 75.736 | under progress | Lift from Tungabhadra River
Filling of 17 tanks in Asundi and adjoining areas | null | null | 2017-12-01 | Rs.79.80 crores | null | null | null | Asundi and 17 surrounding tanks | Ranebennur, Byadagi, Hirekerur | Haveri | 15.7465 | 75.0245 | under progress | Lift from Kumadwathi River
Filling of 32 tanks of Banavasi Hobli | null | null | 2017-12-01 | Rs.62.58 crores | null | null | null | 32 tanks of Banavasi Hobli | Sirsi | Uttara Kannada | 14.6169 | 74.8377 | under progress | Lift irrigation from varada river
Hosalli Tank Filling Scheme | null | null | 2019-08-01 | Rs.250.00 crores | null | null | null | 75 tanks + Anjanapura reservoir | Shikaripura & Shiralkoppa | Shimoga | 12.8774 | 77.5312 | under progress | Lift from local rivers/reservoirs
Filling of 31 MI / ZP tanks of Soraba taluk – Mugur Tank Filling Scheme | null | null | 2019-08-01 | Rs.105.00 crores | null | null | null | 31 MI/ZP tanks | Soraba | Shimoga | 12.1324 | 76.9371 | under progress | Lift irrigation from varada river
Filling of 66 MI / ZP tanks of Soraba taluk – Mudi Tank Filling Scheme | null | null | 2019-08-01 | Rs.285.00 crores | null | null | null | 66 MI / ZP tanks | Soraba | Shimoga | 14.3811 | 75.1028 | under progress | Lift irrigation from varada river
Filling of 186 MI / ZP tanks in Udugani-Talagunda-Hosuru hoblis | null | null | 2019-08-01 | Rs. 850.00 crores | null | null | null | 186 MI / ZP tanks | Shikaripura | Shimoga | 14.3414 | 75.2554 | under progress | Lift irrigation for tunga badra river
Filling of 46 (total 53) MI / ZP tanks in Jagalur taluk | null | null | 2019-08-01 | Rs. 660.00 crores | null | null | null | 53 MI / ZP tanks | Jagalur | Davangere | 14.5214 | 76.3354 | under progress | Lift irrigation for tunga badra river
Filling of 38 tanks in Bharamasagara Hobli and 01 tank in Davanagere taluk | null | null | 2019-09-01 | Rs. 522,11,00,000cr | null | null | null | 39 MI / ZP tanks | Bharamasagara Hobli & Davanagere | Davanagere | 14.3342 | 76.7052 | under progress | Lift irrigation for tunga badra river
Anur Tank Filling Scheme | null | null | 2019-10-01 | Rs. 212,00,00,000cr | null | null | null | 30 tanks of 18 villages | Byadagi | Haveri | 14.7004 | 75.4815 | under progress | Lift irrigation for tunga badra river
Budappanahalli Tank Filling Scheme | null | null | 2019-10-01 | Rs. 157,00,00,000cr | null | null | null | 17 tanks | Byadagi | Haveri | 14.7149 | 75.5746 | under progress | Lift irrigation for tunga badra river
Balambeedu Tank Filling Scheme | null | null | 2019-10-01 | Rs. 386,55,00,000cr | null | null | null | 162 tanks | Hanagal | Haveri | 14.7603 | 75.2148 | under progress | Lift from Varada River
Hirekoushi Tank Filling Scheme | null | null | 2019-10-01 | Rs. 117,55,00,000cr | null | null | null | 77 tanks | Hanagal | Haveri | 14.6489 | 75.1228 | under progress | Lift from Varada River
Sarvagna Tank Filling Scheme | null | null | 2019-10-01 | Rs. 185,00,00,000cr | null | null | null | 77 tanks | Hirekerur & Rattihalli | Haveri | 14.456 | 75.3944 | under progress | Lift from Tungabadra River
Sowkuru Lift Irrigation Scheme | 1350 ha | null | 2019-08-01 | Rs. 73,71,00,000cr | null | null | null | Sowkuru, Karkunje, Kenchanooru, Devalakundkanyana & surrounding villages | Kundapur | Udupi | 13.6471 | 74.7568 | under progress | Lift from Varahi River
Yennehole Lift Irrigation Scheme | 1500 ha | null | 2019-10-01 | Rs. 108,00,00,000cr | null | null | null | Ajekar, Marne, Koranjibailu, Bolthottu, Higana, Devese, Mundhal, Hermade villages | Karkala | Udupi | 13.301 | 74.9924 | under progress | Lift from vented dam
Bennithora Modernisation Works | 20,234 ha | 2 canals | null | null | null | null | null | null | Chittapur | Kalaburagi | 17.4374 | 77.0014 | Nearly completed | null
Bhima Lift Irrigation Scheme | 24,292 ha | null | null | null | null | null | null | null | Afzalpur | Kalaburagi | 16.4042 | 75.6056 | Nearly completed | Barrage & Lift
Gandorinala Modernisation Project | 7,943 ha | Main canal D-18 of Allagi, D-1 of Balundagi | null | Rs. 92,00,00,000cr | null | null | null | null | Kalaburagi | Kalaburagi | 17.5695 | 76.9209 | Under progress | null
Modernisation of Canal Network of Lower Mullamari Project | 9713 ha | null | null | Rs.117.00 crores | null | null | null | Mullamari | Chincholi | Kalaburgi | 17.4673 | 77.4172 | Under progress | null
Amarja Project | 8903 ha (8729 ha provided irrigation) | null | null | null | null | null | null | null | Aland & Afzalpur | Kalaburagi | 17.8626 | 77.3391 | completed | null
Bori LIS | null | null | 2018-02-01 | Rs.450.00 crores | null | null | null | Amarja reservoir & MI tanks | Alnad & Afzalpur | Kalaburagi | 15.7802 | 74.8959 | Under progress | Lift from Bori River
Karanja Project | 29,227 ha | null | null | null | null | null | null | Bhalki, Bidar, Humnabad | Bhalki, Bidar, Humnabad | Bidar | 18.2787 | 77.0961 | Nearly Completed | null
Modernisation works of Karanja Canals | 29,227 ha | null | 2017-11-01 | Rs.482.00 crores | null | null | null | Bhalki, Bidar, Humnabad | Bhalki, Bidar, Humnabad | Bidar | 17.874 | 77.3327 | under progress | null
Supplemental project of providing water from Manikeshwara and Halahalli Barrage between km 60 to 90 of Right Bank Canal to make good the shortage in the inflow of Karanja Reservoir | 29,227 ha | Right Bank Canal km 60–90 | 2017-09-01 | Rs.126.85 crores | null | null | null | Bhalki, Bidar, Humnabad | Bhalki, Bidar, Humnabad | Bidar | 17.8667 | 77.3203 | under progress | null
Upper Mullamari Modernisation Works | 3,279 ha | Main canal (30 years old) | null | Rs.68.60 crores | null | null | null | Humnabad, Basavakalyana, Kalaburgi | Humnabad, Basavakalyana, Kalaburgi | Bidar & Kalaburgi | 17.7116 | 77.0019 | under progress | null
Filling of Chulkinala Reservoir and tanks by lifting water from Kongali Barrage | null | null | 2017-08-01 | Rs.188.00 crores | null | null | null | Chulkinala Reservoir & 15 tanks | Basavakalyana | Bidar | 17.8723 | 76.9465 | under progress | Lift from Kongali Barrage
Modernisation of Tungabhadra Canal Network | 3,62,938 ha | Both banks canals | null | Rs.3161.35 crores | null | null | null | null | Hospet | Ballari | 13.0717 | 77.3984 | under progress | null
Singatalur Lift Irrigation Scheme | 1,07,380 ha (19,587 ha through flow & 87,793 ha through Drip) | Right Bank Canal 40.13 km (completed), Left Bank Canal 166.44 km (under progress) | null | null | null | null | null | Huvinahadagali, Koppal, Yalaburgi, Gadag, Mundargi | Huvinahadagali, Koppal, Yalaburgi, Gadag, Mundargi | Bellary, Koppal, Gadag | 15.0586 | 75.8877 | Right Bank Canal completed, Left Bank Canal drip irrigation works under progress | null
Ola Bellary Lift Irrigation Scheme | 2,542 ha | null | null | null | null | null | null | null | Sindhanur | Raichur | 15.7715 | 76.754 | Nearly completed | null
Modernization Of Vijayanagar Canals | 11,222 Ha | null | null | Rs.456.63 crores | null | null | null |  | Hospet, Shiraguppa, Gangavathi Manvi | Koppala,Ballari | 15.2689 | 76.3918 | under progress | null
Rajoli Banda Project | 2380 Ha | Tungabhadra reservoir | null | null | null | null | null | null | null | nun | 15.9152 | 78.0919 | completed | null
Filling up of 10 Tanks in Huvina Hadagali taluk from Tungabhadra River | null | upstream of Tungabhadra reservoir | null | null | null | null | null | 10 tanks | Huvina Hadagali | null | 15.0204 | 75.9311 | Nearly completed | null
Alvandi Betageri LIS | 2425 ha | null | null | null | null | null | null | null | Koppal taluk | null | 13.1103 | 75.5706 | Nearly completed | null
Filling of Malvi Reservoir in Hagaribommanahalli taluk of Ballari district by Lift Irrigation from Tungabhadra River | 2965 Ha | null | 2017-08-01 | Rs.144.95 crores | null | null | null | Malavi | null | null | 15.0046 | 76.1883 | Under progress | null
Filling of 20 Percolation Tanks by lifting water from Tungabhadra near Itagi village in Shi rahatti taluk of Gadag district | null | null | 2017-07-01 | Rs. 140.00 crores | null | null | null | null | Shirahatti | Gadag | 15.2314 | 75.5774 | under progress | null
Thimmapura LIS | 34984 acres | null | 2018-02-01 | Rs.92.00 crores | null | null | null | Turakatti | Sindhanur | Raichur | 15.8257 | 76.8767 | Under progress | null
Filling of Karadona & Ramadurga tanks | null | null | null | Rs.15.00 crores | null | null | null | Kanagairi | Gangavathy | null | 15.95 | 75.2981 | under progress | null
Bahaddur Bandi LIS | 5256 ha | null | null | ₹188.41 Crores (Total) / ₹80.00 Crores (Stage-1) | null | null | null | Bahaddur Bandi and 18 adjoining villages | null | null | 15.3151 | 76.1624 | under progress | null
Augmentation of Ganekal Balancing Reservoir from Krishna River | null | Tungabhadra Left Bank Canal (LBC) at Mile-109 | null | Rs.189.22 Crores | null | null | null | Ganekal Reservoir | Raichur | Raichur | 16.2372 | 77.1162 | under progress | null
Filling up of 13 tanks and providing drinking water facility to 21 villages in Hospete taluk | null | null | null | Rs.243.35 Crores | null | null | null | 18 Tanks (including 3 percolation tanks) & 4 check dams | Hospete | Vijayanagara | 15.2692 | 76.3906 | under progress | null
Filling of Aladamma Kere in Sugnahalli village in Bannikoppa Gram Panchayati, Shiratti taluk, Gadag district | null | null | null | Rs.10.00 Crores | null | null | null | Sugnahalli & Bannikoppa | Shirahatti | Gadag | 15.1268 | 75.7806 | under progress | null